Vc/6-Sep-04

### Week37 starting 6Sept  04

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday 30 aug04  ~14.20 hrs

| TBA1 | MBBL1126 | Prep 5 Pumping + Cool Down | 302.5 |
| --- | --- | --- | --- |
| TBA2 | MBAL2047 | PT 12 Warm Up | 4.6 |
| TBB1 | SSS035 | FS21 MQ strength@760 | 1.9 |
| TBB2 | _ | _ | 300.3 |
| TBC1 | MBAL3202 | ICS 4 Final connection | 298.6 |
| TBC2 | MBBL1099 | ICS 4 Final connection | 299.2 |
| TBD1 | SSS043 | PT 1 IAP @ cold | 1.91 |
| TBD2 | SSS038 | Finished Ready to go Final scan | 299.7 |
| TBE1 | MBAL3159 | Prep 5 Pumping + Cool Down | 270.1 |
| TBE2 | MBBL3195 | Prep 5 Pumping + Cool Down | 92.8 |
| TBF1 | MBAR1133 | PT 12 Warm Up | 101.5 |
| TBF2 | MBAL3146 | PT 6.1 Training 1 | 26.3 |

9/6/2004 2:20:30 PM    Temperature data are taken from TBSM18 site

Coordinator this week: Marco; MTM support on call :  (16-3602).

11 Magnets [ 9  dipoles( 3 with MM)+ 2 SSS]   Disconnected after tests last week ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

( SSS work : New issues like Wire Breakages

| Magnets under Test from 29-08-2004 to 04-09-2004 LAST WEEK |
| --- |
| - | Bench | Magnet | Shafts | Start Date . | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total |  |  |
| 1 | TBA1 | MBAL3152 |  | 30-08-2004 | 23 h. | 41 h. | 18 h. | 26 h. | 6 h. | 04-09-2004 | 120 hours |  |  |
| 2 | TBA1 | MBAL3199 |  | 23-08-2004 | 28 h. | 53 h. | 34 h. | 28 h. | 7 h. | 30-08-2004 | 168 hours |  |  |
| 3 | TBA2 | MBBL2093 |  | 26-08-2004 | 30 h. | 27 h. | 27 h. | 26 h. | 6 h. | 31-08-2004 | 120 hours |  |  |
| 4 | TBB1 | SSS018 |  | 17-08-2004 | 81 h. | 45 h. | 85 h. | 7 h. | 73 h. | 30-08-2004 | 312 hours |  |  |
| 5 | TBB2 | MBBL3196 |  | 24-08-2004 | 38 h. | 29 h. | 50 h. | 19 h. | 7 h. | 30-08-2004 | 144 hours |  |  |
| 6 | TBC1 | MBAL3145 |  | 25-08-2004 | 33 h. | 65 h. | 68 h. | 25 h. | 0 h. | 02-09-2004 | 192 hours |  |  |
| 7 | TBD1 | SSS044 |  | 18-08-2004 | 152 h. | 47 h. | 83 h. | 12 h. | 23 h. | 31-08-2004 | 312 hours |  |  |
| 8 | TBE1 | MBAL3169 |  | 28-08-2004 | 26 h. | 31 h. | 39 h. | 23 h. | 3 h. | 02-09-2004 | 120 hours |  |  |
| 9 | TBE2 | MBBR1036 |  | 26-08-2004 | 46 h. | 29 h. | 57 h. | 14 h. | 6 h. | 01-09-2004 | 144 hours |  |  |
| 10 | TBF1 | MBAL2057 |  | 22-08-2004 | 30 h. | 60 h. | 42 h. | 35 h. | 13 h. | 29-08-2004 | 168 hours |  |  |
| 11 | TBF2 | MBAR1140 |  | 24-08-2004 | 26 h. | 44 h. | 64 h. | 17 h. | 5 h. | 31-08-2004 | 168 hours |  |  |

### Quench Information last week

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBAL3152 | 12647 A. (D1 L) | 12850 A. (No Data) |  | - | - | - | - | - | - | - | - | - | - |
| 2 | MBAL3199 | 11419 A. (D1-L) | 12653 A. (D2-U) |  | - | - | - | - | - | - | - | - | - | - |
| 3 | MBBL2093 | 11123 A. (D1-U) | 12358 A. (D2-L) |  | - | - | - | - | - | - | - | - | - | - |
| 4 | SSS018 | 11295 A. (QI_12) | 12331 A. (QE_12) |  | - | - | - | - | - | - | - | - | - | - |
| 5 | MBBL3196 | 9805 A. (D2_L) | 11857 A. (D2_L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 6 | MBAL3145 | 10959 A. (D1_U_S01) | 11571 A. (D2-U-S01) | 11781 A. (D2_U_S01) | 11996 A. (D1_U_S13) | 12184 A. (D2 U) | 12477 A. (D1-U-S01) | 12546 A. (D2-U-S01) | 12715 A. (D1-U-S01) | 12850 A. (L0409010) |  | - | - | - |
| 7 | SSS044 | 12067.3 A. (QE-34) | 12856 A. (No Data) |  | - | - | - | - | - | - | - | - | - | - |
| 8 | MBAL3169 | 12648 A. (D1 U) | 12850 A. (No Data) |  | - | - | - | - | - | - | - | - | - | - |
| 9 | MBBR1036 | 11825 A. (D1-L) | 12213 A. (D1-L) | 11950 A. (D1_L) | 12170 A. (D1-L) | 12246 A. (D1_L) | 12382 A. (D1_L) | 12432 A. (D1 L) | 12498 A. (D1-L) | 12760 A. (D2-L) |  | - | - | - |
| 10 | MBAL2057 | 12315 A. (D1-U-S01) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 11 | MBAR1140 | 12465 A. (D1_U, S1) | 12666 A. (D1_L-S13) | 12811 A. (D2-U-S12) |  | - | - | - | - | - | - | - | - | - |

Bench status  and tests for now( Monday 30 Aug/at 17.45 hrs)  & next few days :  see Video Display

General Problems last week :

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_31_A | TBC | LHC cycle measurements: no reading of the Temperature. | MTM |  | Connection still in SSS configuration. Export blocked. Why not detected in MM0? |
| Tuesday_31_A | TBD2 | Powering corrector circuit CD (MCS) : quench well below 600 A. ie 220 A. Same problem for EF (MQT) : 250 A. | ICS? |  | Investigation by Richard. Everything in the quench detection is OK. Wit for the disconnection to seen if everything is properly connected. |
| Tuesday_31_A | TBA2 | HV (WP04) executed by ICS but not available in HVMTF folder. | ICS |  | ICS informed : They executed the export later. |
| Tuesday_31_N | TBD2 | SSW at cold : strength measurements Message “checking motion status” displayed continuously. Test re-launched: but unable to adjust the wire tension. Test re-launched : wire broke. | MTM |  | Richard contacted: he tightened a screw. |
| Wednesday_01_A Wednesday_01_N Wednesday_01_N | TBD2 | SSW measurements : SPA abort appeared. Difficulties to re-start TEMA: power App was hung SPA again (2 times) during SSW measurements at cold Wire broke again during roll angle measurements | AB-CO | Power | Re-start work-station and re-start TEMA several times. |
| Wednesday_01_A | TBB1 | Power QH OK interlock was not clearing | MTM |  | Richard called Origin: Configuration for protection not the same for SSS (TBB) and dipoles (TBB2) with two circuits in instead of 4. So even the PS are charged the PLCSE is not OK when we switch to SSS because 2 circuits are opened. OK when you connect the channels 2 and 3 to dummy resistance. |
| Wednesday_01_A | TBB1 | IAP@warm : polarity on Vtaps inverted. | MTM |  | Error in DAQ templates found by Richard. |
| Thursday_02_A | TBC | PLC fault through the switch is in CC position | MTM |  | Solved by Gorgio |
| Thursday_02_A | TBF | Tcoil (IAP): wrong values Problems in coils 0405 –A and coils 1213-E. | MTM |  | Richard informed :Tcoil calibration data missing in MTF Richard changed the setting using E coil for 0405 sector |
| Thursday_02_N | TBD2 | SSW error message (“too many”) after typing the command “menu” | MTM |  | Richard found that the “db. seriesRun” file had a wrong variable name. |
| Thursday_02_N | TBD2 | Wire broke during rotwire. | MTM |  | OP team waited until the program stopped but the wire still try to stretch the broken wire by turning the motor, |
| Friday_03_N Saturday_04_M | TBD1 | SSS038: HV test failed orbit dipole vs ground at 1500 V (OK at 300 V). | MTM |  | Confirmed by Richard. NC opened., |
| Sunday_05_A | TBB1 | SPA occurred during XY measurements on SSS035 (2 times). Then wire broke during XY measurements. | MTM |  |  |
| Sunday_05_A | TBC2 | IAP @ warm: QH could not be charged. Trigger always present. | MTM |  | Richard called. |
| Sunday_05_N | All benches | General cut of power: (failure in the meyrin site) Cryo down. |  |  | Power back at midnight. |