Vc/29-Mar-05

### Week 12 starting 21 Mar. 05

### SM18 Operation Meeting (Tuesdays)

Bench status on Tuesday 22 morning.

| 12 | A1 | MBBL1196 | Prep 1 Lyre Test | 295.18 |
| --- | --- | --- | --- | --- |
| 2 | A2 | MBBR3275 | PT 6.1 Training 1 | 4.55 |
| 3 | B1 | SSS602 | Survey @ Cold SC24 | 1.90 |
| 9 | B2 | MBAL1202 | Prep 5 Pumping + Cool Down | 95.7 |
| 10 | C1 | MBAL2155 | Prep 3 CDW1 HV | 294.64 |
| 11 | C2 | MBBL1165 | CR 1 Leak Test | 295.18 |
| 1 | D1 | SSS103 | PT 13.2 Resist. Meas. | 296.43 |
| 6 | D2 | SSS019 | Prep 5 Pumping + Cool Down | 294.73 |
| 8 | E1 | MBBR3294 | PT 12 Warm Up | 298.58 |
| 4 | E2 | MBBR3293 | ICS 6 Disconnect Magnet WP07 | 299.2 |
| 5 | F1 | MBAL1203 | PTE Min. NRJ 3KA Diode Test | 1.90 |
| 7 | F2 | MBAL2101 | Prep 5 Pumping + Cool Down | 2.35 |

- Coordinator this week: Vittorio Remondino;

- MTM support on call : Maryline Gateau .

- 15  Magnets Tested    :10  dipoles ( 2 with MM, MB3127, MB3284 special test) + 3  SSS ( 1 – Only  HV Test (SSS36), 1- Thermal cycle (SSS129) , 0  with MM) +  1  SSSS (SSS601)

Disconnected after tests last week ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- Situation From Mechanics:  J.Halik

- SSS:  N.Smirnov.

-SSW meas. on SSS601.

- 3rd system.

- AOB:  Status of HV rack (Richard), AQA (Marco).

| Magnets under Test from 13-03-2005 to 19-03-2005 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total |  |  |
| 1 | TBA1 | MBAL3144 |  |  | 11-03-2005 | 18 h. | 24 h. | 24 h. | 15 h. | 9 h. | 14-03-2005 | 90 h. |  |  |
| 2 | TBA2 | MBAR3258 |  |  | 13-03-2005 | 20 h. | 24 h. | 23 h. | 23 h. | 12 h. | 18-03-2005 | 102 h. |  |  |
| 3 | TBA2 | MBBL3127 |  |  | 08-03-2005 | 35 h. | 28 h. | 36 h. | 22 h. | 8 h. | 13-03-2005 | 129 h. |  |  |
| 4 | TBB1 | SSS601 |  |  | 28-02-2005 | 62 h. | 20 h. | 158 h. | 30 h. | 60 h. | 14-03-2005 | 330 h. |  |  |
| 5 | TBB2 | MBBL2143 |  |  | 09-03-2005 | 28 h. | 34 h. | 15 h. | 25 h. | 22 h. | 14-03-2005 | 124 h. |  |  |
| 6 | TBC1 | MBAR3256 |  |  | 13-03-2005 | 24 h. | 29 h. | 20 h. | 18 h. | 7 h. | 17-03-2005 | 98 h. |  |  |
| 7 | TBC1 | MBBL3155 |  |  | 09-03-2005 | 21 h. | 26 h. | 15 h. | 15 h. | 7 h. | 13-03-2005 | 84 h. |  |  |
| 8 | TBC2 | MBAR3297 |  |  | 11-03-2005 | 26 h. | 33 h. | 49 h. | 17 h. | 7 h. | 16-03-2005 | 132 h. |  |  |
| 9 | TBD1 | SSS036 |  |  | 09-03-2005 | 60 h. | 57 h. | 52 h. | 16 h. | 18 h. | 18-03-2005 | 203 h. |  |  |
| 10 | TBD2 | SSS129 |  |  | 06-03-2005 | 50 h. | 24 h. | 66 h. | 11 h. | 0 h. | 13-03-2005 | 151 h. |  |  |
| 11 | TBD2 | SSS129 |  |  | 13-03-2005 | 0 h. | 1 h. | 17 h. | 10 h. | 22 h. | 15-03-2005 | 50 h. |  |  |
| 12 | TBE1 | MBAR3255 |  |  | 08-03-2005 | 30 h. | 32 h. | 40 h. | 20 h. | 8 h. | 14-03-2005 | 130 h. |  |  |
| 13 | TBE1 | MBBR3263 |  |  | 14-03-2005 | 38 h. | 31 h. | 17 h. | 15 h. | 12 h. | 19-03-2005 | 113 h. |  |  |
| 14 | TBE2 | MBAR1046 |  |  | 12-03-2005 | 30 h. | 26 h. | 28 h. | 18 h. | 13 h. | 17-03-2005 | 115 h. |  |  |
| 15 | TBF1 | MBAR3284 |  |  | 10-03-2005 | 30 h. | 24 h. | 114 h. | 29 h. | 13 h. | 19-03-2005 | 210 h. |  |  |

### Quench Information

### Week  13 Mar 05 to 19 Mar 05

Thermal Cycle		HV Tests @ Cold

Light green: Connect + Pump down 	Blue :  Wait + Cool down

Ivory: Tests at Cold (36 hr)			Red :  Wait + Warm up (12 hr)	    Dark Green: Disconnect (8 hr)

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday _15_M | TBF1 | Air leak in the CFB: quench recovery difficult. | ACR |  | J.P Lamboy managed to solved the problem: re-start of the extended test ½ day after. |
| Tuesday _15_A | TBC1 | communication problem between local sun server and PLC | AB/CO? |  | OK after restarting server process on local sun station downstairs |
| Tuesday _15_A | TBA1 | A1 anticryostat problem | ICS |  | Solved by Salem: bad connections |
| Tuesday _15_A | all | unable to log in to HV Test application (error message: "The user name does not exist") | AB/CO |  | M.Marchesotti solved the problem: The user server at 17.30 started distributing an empty Users.cfg file. User server stopped and the configuration files were distributed manually to all the workstations. |
| Tuesday _15_N | TBF1 | Error at CPU adress and Acquisition trigger not received Error on motor unit 2...Test Aborted during the cycle.. | MTM |  | Salem called. Intervention of Frederic and Patrick. The end stop detection was not working properly in aperture 2. The shaft went into the mechanical end stop and the clutch was slipping. |
| Thursday _17_M Thursday_17_A Thursday_17_N | TBD1 TBA1 | XMT.MY 95 HV rack connector is faulty (passive/active bus bar) XMT.MY 93 HV rack did not work The magnet name was not correct. XMT.MY 92 HV rack did not work The magnet name through bench selection is not working | ICS |  | Repair is needed. Done by Fabienne Friday. Changed over to XMT.MY95. Name entered manually. |
| Tuesday _15_N | TBD1 | WP17 : launched using XMT.MY 95 HV (authorisation of Salem): wrong polarity in the setting | MTM |  | Salem asked to lunch the test with the repeat option.. |
| Tuesday _15_N | TBF1 | Rocla did not work: it impeded ICS team to remove the shafts from the 3284 magnet | ICS |  | Shift leader asked to cryo team to stop the warm up. TC informed. TC asked the cryo team to put at least the magnet in stand by. Comment: if the magnet cannot be put in stand by do not cool it down again : the shafts will be removed at warm by MTM mechanics. |
| Tuesday _15_N | TBD2 | SSS128: Problem in the extension number of training quenches: a02 for quench1 and a04 for quench 2. | MTM |  |  |
| Friday _16_M | TBD2 | SSS 128: Config Error when launching next training quench ´Error in DB while executing hr_confgen´ | MTM |  | Salem informed. |
| Friday _16_M | TBA1 | IAP at cold repeated on 1184 magnet as it was carried earlier with Q-Loc cable connected for LQA & not for shaft.. | MTM |  | Salem connected the right cable for long shaft and test was repeated |
| Friday _16_M | TBA1 | Magnet quenched at 12681 A. AQA analysis of file .zb01 shows an alert that QH heaters were not charged though they were charged and discharged also as a result of this quench. | MTM |  |  |