### Week 25 starting 19 June 06

### SM18 Operation Meeting (Tuesdays) 13 June 06

Bench status  on Monday  19-06-2006 at:  6/19/2006 9:51:35 AM

| 1 | A1 | MBBR2290 | Extra min. Energy test | 1.90 |
| --- | --- | --- | --- | --- |
| 4 | A2 | MBAL 2569 | Prep 0 Scan Bench | 299.65 |
| 6 | B1 | SSS319 | Prep 5 Cool Down | 2.35 |
| 8 | B2 | SSS678 | PT 6.2 Training 2 | 4.25 HV |
| 2 | C1 | SSS185 | PT 13.1 IAP @ Warm | 296.79 |
| 11 | C2 | SSS340 | Prep 5 Cool Down | 4.68 HV |
| 12 | D1 | SSS659 | Waiting for Disconnection | 298.67 |
| 9 | D2 | SSS532 | PT5.3: Powering Corrector CD | 1.90 |
| 7 | E1 | MBAR1357 | PT 9 CDAP HV | 1.90 |
| 10 | E2 | MBAR1300 | PT 3 QH Measure | 1.90 |
| 3 | F1 |  |  | 298.67 |
| 5 | F2 | MBAR1292 | ICS 4 Final connection | 298.76 |

CONFIG :  D6- AS3 –IRSSS3;

Supervisor: Gijs (gilbert)/        Eq support : 16-3602 :

11 Magnet Tests completed :  8 Dipoles (),  1 Arc-SSS  ( 038  REPEAT)

(11 Magnets in all)		1  500-series ( 532 (  HV tests failure…

1  600-series [ 649 (153 hrs),  ( hrs),    ]

2262 worked as expected after Th Cycle & reached 12850A in 3 ramps

( total 204 + 93 = 297 hrs = ~ nearly 2 weeks   )

General Points :

532 ( MQ) seems to quench Sun night in busbars ? 3 quemches @  ~ 7K A

D1 659 could have been warmed up on Thursday & removed Friday or Sat  (

### B1   was under repair early in week;          C1 & C2 were converted to SSS starting 12June ; C2 on Monday & C1 on Thursday( comment last Monday not valid – we efficiently used weekend + to fully use the bench & finish a dipole 1332 in 110 hrs, so sat to Thursday ) ; anyway, Lionel had only 1 mech on Monday to handle B1 first…

- Situation from Cryogenics:  J-P Lamboy or ACR Rep.

- News /Situation from (SSS, SSSS)  :  J Halik

- Situation SSSS  :OP issues :

A.O.B..

| Magnets under Test from 11-06-2006 to 17-06-2006 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |  |  |
| 1 | TBB2 | SSS649 |  |  | 09-06-2006 | 70 h. | 14 h. | 50 h. | 8 h. | 11 h. | 16-06-2006 | 153 h. | Stand By |  |  |
| 2 | TBC1 | MBAR1332 |  |  | 10-06-2006 | 46 h. | 27 h. | 15 h. | 13 h. | 9 h. | 15-06-2006 | 110 h. | Stripping |  |  |
| 3 | TBC2 | MBAR1291 |  |  | 08-06-2006 | 32 h. | 28 h. | 23 h. | 17 h. | 6 h. | 12-06-2006 | 106 h. | Stripping |  |  |
| 4 | TBC2 | SSS350 |  |  | 13-06-2006 | 38 h. | 16 h. | 24 h. | 7 h. | 15 h. | 17-06-2006 | 100 h. | Stripping |  |  |
| 5 | TBD2 | SSS532 |  |  | 08-06-2006 | 113 h. | 25 h. | 7 h. | 10 h. | 16 h. | 15-06-2006 | 171 h. | Stand By |  |  |
| 6 | TBE1 | MBAR2329 |  |  | 11-06-2006 | 35 h. | 31 h. | 18 h. | 15 h. | 18 h. | 16-06-2006 | 117 h. | Stripping |  |  |
| 7 | TBE1 | MBBR2302 |  |  | 06-06-2006 | 28 h. | 25 h. | 16 h. | 15 h. | 14 h. | 11-06-2006 | 98 h. | Stripping |  |  |
| 8 | TBE2 | MBAL2343 |  |  | 12-06-2006 | 29 h. | 31 h. | 24 h. | 15 h. | 13 h. | 16-06-2006 | 112 h. | Stripping |  |  |
| 9 | TBE2 | MBAR1355 |  |  | 07-06-2006 | 24 h. | 25 h. | 18 h. | 14 h. | 19 h. | 11-06-2006 | 100 h. | Stripping |  |  |
| 10 | TBF1 | MBAL2339 |  |  | 09-06-2006 | 32 h. | 26 h. | 25 h. | 14 h. | 10 h. | 13-06-2006 | 107 h. | Stand By |  |  |
| 11 | TBF2 | MBBR2262 |  |  | 10-06-2006 | 32 h. | 10 h. | 18 h. | 24 h. | 9 h. | 13-06-2006 | 93 h. | Stripping |  |  |

### B1 was under repair early in week; C1 & C2 were converted to SSS starting 12June

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | SSS649 | 3938 A. (Int_MQML) | 4132 A. (E-MQML34) | 4216 A. (Ex-MQ-34) | 4278 A. (E-MQML12) | 4334.3 A. (MQML_12) | 4367.6 A. (MQML_12) | 4417.9 A. (MQM_34) | 4453.1 A. (Ex_MQM12) | 4466.4 A. (In_MQM34) | 4482.9 A. (E-MQML34) | 4627.5 A. (E-MQML34) | 4652 A. | - |
| 2 | MBAR1332 | 11578.7 A. (D1_L) | 12696.2 A. (D2_L) | 12757.3 A. (D2_U) |  | - | - | - | - | - | - | - | - | - |
| 3 | MBAR1291 | 11944.4 A. (D1_U) | 12476.7 A. (D2-U) | 12641.6 A. (D1-L) |  | - | - | - | - | - | - | - | - | - |
| 4 | SSS350 | 12174.7 A. (QE-12) | 12214 A. (QI_12) | 12653.5 A. (QI_34) |  | - | - | - | - | - | - | - | - | - |
| 5 | SSS532 |  | - | - | - | - | - | - | - | - | - | - | - | - |
| 6 | MBAR2329 | 12114.7 A. (D2_U) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 7 | MBBR2302 | 10987 A. (D1_U) | 12096.4 A. (D2_U) | 12285.1 A. (D1_U) |  | - | - | - | - | - | - | - | - | - |
| 8 | MBAL2343 | 11882.6 A. (D1_U) | 12150.1 A. (D1_U) | 12749 A. (D1-U) |  | - | - | - | - | - | - | - | - | - |
| 9 | MBAR1355 | 12311.1 A. (D1_U) | 12849.1 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 10 | MBAL2339 | 10908.1 A. (D2-U) | 11639.3 A. (D2-U) | 12524 A. (D2-U) | 12590.8 A. (D2-U) |  | - | - | - | - | - | - | - | - |
| 11 | MBBR2262 | 11633.3 A. (D1_L) | 12336.6 A. (D1_L) | 12853 A. | - | - | - | - | - | - | - | - | - | - |

Effective  only 11 magnets Tests this week ; 649  usual long connection times & long training; 532 had warm SSW & then HV pblms & so was disconnected & only after the  problem reason defined – so now connected & tested again in week 19 June

2262 was AFTER ROBTC,

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_13_M Tuesday_13_A | TBA1 | MB2290: TRU Shaft on Ap1 is to be moved by hand The steering wheel is out of service MB2290: Special MM program : training quench between the two machine cycles is OK? | MTM |  | TRU changed by MTM mechanics. Test program: Stephane advised to repeat MM1 and to do MM3 directly without repeating MM2. Stephane answered that any quench equal or above 6.5 kA is OK. For provoked quenches , shaft stayed in MM position. For training quench move the shaft in Qloc position and then back to MM position.. |
| Tuesday_13_N | TBB2 | SSS649: AQA Alert for training ramp#5, MITS value exceeds 2.3 for I = 4.3K. | MTM | AQA | TC informed to continue. |
| Tuesday_13_N | TBC1 | MB1332 : When PT9 was launched with HV rack MY93, during the first step 'dipole QH vs ground' 600V was continuously being applied for more than 300 sec, whereas the actual duration would have been 120 sec. | AB/CO | HV | Megger problem. Removed by Richard. |
| Tuesday_13_N | TBC | MB1332: Application 'hfoff' in the sun station sunmta23 is not permitting manual MIITS calculation. | AB/CO | hf |  |
| Tuesday_13_N | TBA1 | MB2290 : During LHC_cycle_300s special MM test, a detraining quench ( by 1 kA) occurred at 11850 A. | MTM |  | Stephane informed. He advised to re-train the magnet and then repeat the LHC_cycle_300s. |
| Tuesday_13_N | TBC2 | SSS350: Dipole to SSS conversion problem. All the quench heater connections are carried to the bench. Unable to connect two quench heaters to the dummy resister due to permanent connection to bench. | MTM |  |  |
| Wednesday_14_M | TBD2 | SSS532 : Insulation Test Failure on the MQTL. Magnet. | MTM |  | Equipment Support contacted. Problem under investigation. NC Generated in CQBP. The report file will be edited and uploaded by Richard.Magnet warm up and investigation by J.Kosak. IFS box detached. A.Siemko found that a cryo-flexible was touching the current leads. The magnet is cooled down again. |
| Wednesday_14_N | TBB1 | SSS319 : LF acquisition is not getting triggered on during clamp connection test (prep 2.2c - CD as well as EF). | ICS |  | OP team asked ICS to re-check the connections on our request, but problem still persists. S4 in TBB2 with not corrector circuit CD. |
| Wednesday_14_N | TBA1 | MB2290 : No data after min. en. 6,5 kA, VME crates :MIXI error, sunmta31 was blocked. | AB/CO |  | Crate switched off/on’ Sun-MTA 31 always blocked, reboot again, but error MIXI still there. Reset the 3 crates 5 times and finally ok!!! |
| Wednesday_14_N | TBA1 | MB2290 : MIXI error during LHC cycle, crate 3 is showing 0 V (overheat)instead of 5 V | MTM |  | Changed by Giorgio. |
| Wednesday_14_N | TBE1 | MB2343 : Files generated during PT 5.1, PT 5.2 and PTE couldn't be accessed from the sun stations in the control room.. Manual MIITS calculation is pending. Problem couldn't be solved even on resetting PLCSE and restarting applications. | AB/CO |  | The files were accessible from local sun station and the local AQA analysis indicated no alarms, and all graphs were OK Equ.support looked into the problem Thursday. Files from not copied because the script is on the sunMTA24 and the sun was switched off. |
| Thursday_15_A | TBF2 | MB1320: Scanning of TRU and shafts. There is a problem with the wireless network. Both mobic cannot access the server. | IT |  | Giorgio will contact Netops for the wireless network. Scanning of TRU, shafts & mobile rack done manually and entered in MTF manually |
| Thursday_15_N | TBE1 | MB2329 : WP07 was done and OK but not getting transferred to HVMTF. So not uploaded. But stripping signed. | MTM |  | Inform Richard about this problem. |
| Friday_16_M | TBC2 | SSS350 : Powering of IJ corrector give a fault | AB/PO |  | New power converter. It has to be commissioned. |
| Friday_16_M | TBF2 | MB1320 : MM2 exportation data in the DB could not be done.” Field 7 not correct”. | AB/CO |  | Stephane informed by Richard. Problem already seen. He advised to warn Guy who will manually change the file configuration. |
| Friday_16_M | TBA1 | MB1320: MM special LHC cycles. Over-range appearing in the head of aperture 1 at high current. | MTM |  | Stephane informed by Giorgio. He advised to proceed as the goal of the special test is to investigate the behavior at around 760 A. |
| Friday_16_A | TBD2 | SSS532: V-Clamp EF faults. | MTM |  | V-taps inversed on the plate-forme. |
| Friday_16_A | TBE1 | MB1357 : Problem with interconnection box during prep.1, PLC blocked. Same problem with prep.2. | MTM |  | Test carried out by re-setting the PLC PLC reset again.TEMA shows "error in DB while executing hr_configuration" |
| Friday_16_N | TBD2 | SSS532: Special test carried out by expert. File no. A0606161831.he01 went to MQLAD_532_2 by mistake. | AB/CO | LF | OP team informed. The extension of the file has also to be changed. Equip.support will correct this. |
| Saturday_17_M | TBD1 | SSS659 : TT821 gave wrong value. | MTM |  | NC opened. |
| Saturday_17_A | TBC1 | SSS185 : Powering of the corrector in the EF circuit is not possible. | AB/PO |  | Salem called AB/PO piquet. Rest of the log file of the PC.. |
| Saturday_17_A | TBC1 | SSS185 : During the Powering of the corrector in the GH circuit , the current in IJ is ramping and vice-versa. | MTM |  | Salem informed. |
| Saturday_17_N |  | Problem with editing the e-logbook. SMTMS web page cannot be read (problem with internet explorer). |  |  |  |
| Saturday_17_N | TBB1 | SSS319: Anticryostat alarm. Magnet in stand-by | MTM |  | Salem informed. He checked and called P.Legrand. Value of the resistance use for temperature reading is wrong, so blocking the coo-down. Problem solved.. |
| Sunday_18_A | TBC1 | SSS185: One quench heater power supply is damaged. | MTM |  | Salem investigated the problem.. He changed the power supply and discharge the heaters in the dummy resistors. |
| Sunday_18_N | TBD2 | SSS532 : PT1 (IAP at cold) errors reported in QI_34-12 : offset 13.6 (max 10.0)) It was not possible to do adjustment on potaim card. | MTM | IAP | Salem informed. The faulty potaim card was replaced. |
| Sunday_18_N | TBC1 | SSS185 : IAP at warm after cold test could not be done because of LF Acquisition Error: MXI error. | AB/CO | lf | Salem solved the problem Monday Morning. |
| Monday_19_M | TBB2 | SSS678 : AQA alert 'MIITS AQA exceeds 2.5 for I=5.1kA' MIITS value=3.7 | MTM | AQA | TC contacted. He advised to ignore the alert and proceed with test. |
| Monday_19_M | TBD2 | SSS532 : 3 training quenches not detected by AQA with quench current value decreasing from 8749A (1st quench) to 7554A (3rd quench). TC anticipated problem in busbar connection. | ACR |  | TC contacted. Training stopped and investigations. Third quench faulty because of not enough cool down. |
| Monday_19_M | TBA1 | MB2290: LHC cycle FT _cur8kA_300s stopped because of cryo_OK lost. | ACR |  | Salem and TC informed. Min NRJ repeated. LHC cycle repeated. |
| Monday_19_A | TBB2 | SSS678: MQ reached ultimate but when launching SPA from TEMA, the sequence was blocked. | MTM |  | Salem informed. |