### VC- /Week 5 starting   27 Jan 07

### SM18 Operation Meeting (Tuesdays) 5 Feb  07

Bench status  on Monday 5-February-2007 at 2/5/2007 11:13:27 AM

| 7 | A1 | MBBR2263 | PT 13.2 Resist. Meas. | 295.18 |
| --- | --- | --- | --- | --- |
| 1 | A2 | MBAR2326 | PT 12 Warm Up | 123.21 |
| 8 | B1 | SSS361 | Finished Ready to go Final scan | 294.91 |
| 5 | B2 | SSS531 | ICS 4 Final connection | 295.8 |
| 9 | C1 |  |  | 293.83 |
| 4 | C2 | SSS356 | PT 13.2 Resist. Meas. | 295.8 |
| 10 | D1 | SSS529 | Prep 5 Cool Down | 295.36 |
| 11 | D2 |  |  | 294.91 |
| 2 | E1 | MBBR2424 | PT 12 Warm Up | 5.95 |
| 12 | E2 | MBBR2426 | Prep 0 Scan Bench | 294.91 |
| 6 | F1 | MBBR2425 | ICS 3 Traveller after warm test | 294.1 |
| 3 | F2 | MBAR2267 | MM3 Full Load Line | 1.9 |

CONFIG :  D 6 - AS 2 -  IRSSS 4 ;

| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | TBD1 | SSS523 |  |  | 10-01-2007 | 147 h. | 13 h. | 63 h. | 61 h. | 215 h. | 31-01-2007 | 499 h. | Stand By |
| 2 | TBF1 | MBAR2328 |  |  | 19-01-2007 | 97 h. | 26 h. | 28 h. | 16 h. | 98 h. | 30-01-2007 | 265 h. | Stripping |

Supervisor: Stephan

Only 2  Magnet Tests completed;

1 Dipole tests (2328, signed for stripping)

1 500 series (523, EF corrector powering failed (18 attempts), natural warm-up)

General Points:

- SSS523 waited for disconnection for 9 days

- Special tests on SSS 356 (C2) and MBAR 2326 (A2) finished

- Special tests on MBAR 2267 (F2) in progress

- Cryo leak problem in MBBR 2425, rectified

- MBBR 2424 on E1 could not be warmed up on Friday (2 Feb) evening

- Eric, Kevin, GHH, Florence, JeromeA  absent 2 Feb to 18 Feb 2007

Situation from Cryogenics:  J-P Lamboy

Situation  all SSS  : J Halik :

TERMINATION COUNTER - 2007

| No | MAGNET | BENCH | ARRIVAL | DEPARTURE | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | 2424 | E1 | 25-01-2007 |  |  |
| 2 | 2326 (MM) | A2 | 19-01-2007 |  |  |
| 3 | 2267 (MM) | F2 | 25-01-2007 |  |  |
| 4 | 2425 | F1 | 30-01-2007 |  |  |
| 5 | 2426 | E2 | 05-02-2007 |  |  |
| 6 | 2394 |  |  |  |  |
| 7 | 2790 |  |  |  | Spare |
| 8 | 2624 |  |  |  | Spare |
| 9 | 2598 |  |  |  | Spare |
| 10 | 2420 |  |  |  | Spare |
| 11 | 2419 |  |  |  | Spare |
| 12 | 2418 |  |  |  | Spare |
| 13 | 2399(MM) |  |  |  | Spare |
| 14 | 2551 |  |  |  | Spare |
| 15 | 2739 |  |  |  | Spare |

6 of  15 Dipoles for completion of Tunnel                 				 Updated : February 13, 2007

Note :

1)   The red line shows the completion of magnets for tunnel.

SICK DIPOLES

| No | MAGNET | Problem due to |
| --- | --- | --- |
| 1 | 1334 | CDBP: QH Vs Gnd |
| 2 | 2324 | NC on capillary |

TERMINATION COUNTER - 2007

| 16 | SSS 531 | B2 | 31-01-2007 |  |  |
| --- | --- | --- | --- | --- | --- |
| 17 | SSS 529 (MM) | D1 | 01-02-2007 |  |  |
| 18 | SSS 530 |  |  |  | 01-02-2007* |
| 19 | SSS 356 | C2 | 25-01-2007 |  |  |
| 20 | SSS 374 |  |  |  | 26-01-2007* |

6 of  6 SSSs for completion of Tunnel

Updated : February 13, 2007

* Expected Arrival Date ( Bldg 904 information)

SICK SSS

| No | MAGNET | Problem due to |
| --- | --- | --- |
| 1 | SSS 523 | MQ inter-turn short |
| 2 |  |  |

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_30_A | TBA2 | MB 2326 : Removal of shafts. Shafts 25-26 frozen. | MTM | IT ACR MTM | Stéphane asked for investigation. Oracle bug which impedes to charge AC coefficient from MTF to PLC. Magnets considered by cryo team as without AC. AC never warmed from the beginning |
| Wednesday_31_M | TBF1 | MBBR2425 During IAP at Warm voltage for diode found reversed. | MTM |  | Giorgio has been contacted; |
| Thursday_01_M | TBF2 | MBA2267: Shaft installed. Waiting for e-traveller signature by ICS. HV test done by OP team any way. | MTM |  | E-traveller could not be signed by ICS because the person understanding English is not available. |
| Thursday_01_M | TBF1 | MBA2425: Leak found at warm during capillary check | ICS |  | Magnet re-opened, joint changed. |