Memo

To:	Whoever It  May Concern

From:	V. Chohan, on Behalf of SM18 Operation Team

CC:	SM18 Op team (Indian Collaborators, AB-OP staff in SM18)

Date:	30 May 2006

Re:	SM18 Magnet Tests in 2006 and Prognosis for Completion

_________________________________________________________________________

1.  DIPOLES  :    We would finish LHC machine required Dipoles  by end 2006 relatively easily

Total outstanding Dipoles on 20 May 06 + ~10 % = (206+20) = 226 Dipoles

At the rate of 36 Dipole Tests per month from 6 Benches gives [226/36] = 6 months to finish from 1-June to

1 –Dec-06 ;    Need to DEDICATE 6 Benches :A1, A2, E1, E2, F1, F2  for DIPOLES

2.  Arc-SSS & Special SSS Considerations together : remaining 86 Arc-SSS,   66 SSSS

( Data source:  Op Tests Management System, SMTMS ) :

(a) Simplest Calculation based on average  on-bench times taken for testing these magnets upto now as well as on-bench times taken for normal Arc-SSS’s. ( 7.19 days Arc-SSS, 9.43 days SpecialSSS )   Assume we have to use 6 benches for all arc-sss’s, 500-series & 600-series Magnets,  i.e., all SSS’s together (while other benches are dedicated for Dipole Tests till Dec 06). Based on this broad average  over 6 benches for all SSS’s, we can only finish all the remaining 86 + 10% = 95 arc-SSS’s & 66 Special SSS’s in 228 days from 20May06 – meaning we are in the first week of January 2007. So,  further detailed  study is required.

(b) Treating only the remaining arc-SSS’ separately first:

Total Outstanding Arc-SSS on 20 May 06 + ~10% = (86+9) = 95 Arc-SSS’s

At the rate of 14 Arc-SSS’s per month from 2 Benches ( C1, C2) gives [95/14] = ~6.8 months or 203 days to finish from 20-May-06 to 8-Dec-06 ; this rate is optimistic and if the rate is bit less, we will have spare capacity on another Cluster B (see below) during and with the 44 Special SSS’s handled by ICS without MM. ( normal rate is closer to 26 arc-SSS’s per month from 2 benches)

Need to Dedicate at least 2 benches C1, C2 for Arc-SSS’s  to terminate ALL Arc-SSS’s  by end-2006

3. Treating Special SSS’s ( 500 & 600 Series) in the light of above

Further detailed refinement of using only B cluster for easy, ICS-supported, non-MM, SSSS magnets (44 magnets) and D cluster for complex SSSS ( 22 magnets) with MM & non-ICS support still leads to  ~197 days for D cluster termination, i.e to early Dec 2006. (see attached tables). Of course , this assumes that right type of special SSS ‘s are available to be tested as required in appropriate types matching appropriate bench usage.( not having this assumption only complicates matters) ; The B cluster 44 magnets would be terminated by mid-Oct 06 , leaving spare capacity for off loading Arc-SSS’s (  2(b) above) or Dipoles as the need may be then, till Dec 06

CONCLUDE : It is the opinion of the OP Team that all the different projections show us to be heading too close to the limits or, that it would NOT be possible to finish the magnet tests by Christmas 2006;  corrective measures would have to be taken now – particularly in bench configurations as well as cryostating all SSS’s (and possibly more Dipoles) so as to not meet further hard limits of staffing & the necessary Cryo Plant Preparation for LHC & Shutdown for end of 2006/ early 2007. We are already at the stage where experienced departing staff are not anymore replaced (11 Indian Associates depart between 7July & 23 Oct 06 – the Indian Collaboration for magnet tests is already in its last phase now).  Hence presently available testing capacity should not be under-used leading to problems later. BENCHES C1, C , B1, B2, D1, D2 ARE ALL REQUIRED from NOW ON for SSS/SSSS Testing.

DETAILS OF ANALYSES

(a) SIMPLE CALCULATION

| Average all SSS | 7.60 | days |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Average Special \ SSS | 9.43 | days |  |  |  |  |  |  |  |  |
| Average Normal SSS | 7.19 | days |  |  |  |  |  |  |  |  |
|  |  | 86 | Normal SSS * | 7.19 | = | 618.35 |  | 1240.92 | / | 6 | benches |
|  |  | 66 | Special SSS * | 9.43 | = | 622.57 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 206.82 | days |  |
|  | Taking percentage Repeats: |  |  |  |  |  |  |  |  |  |  |
|  |  | 95 | Normal SSS * | 7.19 | = | 683.07 |  | 1371.66 | / | 6 | benches |
|  |  | 73 | Special SSS * | 9.43 | = | 688.60 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 228.61 | days |  |
|  |  |  | 20 May 2006 |  |  |  |  |  |  |  |  |
|  |  |  | Upto 17 December 2006 |  | 212 | days |  |  |  |  |  |

(b) More Refined Calculation :  based on appropriate Bench assignment dependent on a particular magnet of 500 or 600 series and using exclusively D & B benches specifically converted for these magnets

Using the attached table and ASSUMING RIGHT MAGNETS ARE AVAILABLE AS NEEDED,

(b1) All Magnets which implicates only ICS for connections/disconnections (totalling 44) can

be finished in  137 Days from 20 May 06, i.e., about 4.5 months or by about mid-Oct 2006

(b2) All the remaining 22 magnets needing MTM Mechanics support, magnetic M’ments etc

May be optimistically be tested in roughly 197 days from now, or rather by roughly first

week in Dec 2006.

(c)  Another calculation based on “mixed” mode bench usage from 2006 (see table attached for D cluster ‘mixed’ mode usage as has been the case so far in 2006).

Scale up ~8 ‘difficult’ magnets in D1 & ~18 ‘easy’ ones on D2 in 4 months gives for SIX months( 2 June to 2  Dec )  12 Magnets tested in D1 and 27 in D2; Apply the same ‘mixed’ mode regime in B Cluster gives us the overall TOTAL 24 ‘difficult’ ones completed and 54 ‘easy’ ones completed. However, there are only 66 outstanding SSSS’s, (of which ~24 are ‘difficult’ ones), so 12 of the easy ones effectively could be arc-SSS’s. Hence, 95-12=83 Arc-SSS’s would still remain to be done from C cluster of 2 benches in SIX months;  At  the current average of ~13 Arc-SSS’s per month from 2 benches, we get (13 x 6= 78) magnets with 5 remaining  ones done in two weeks after 2 Dec 06 to finish before 17 Dec 06.  [ We would  be JUST-IN-TIME (!) for  shutdown to start after 18 Dec 06] .

Generally, IF ONE CANNOT PROVIDE THE RIGHT CRYOSTATED ELEMENTS AT APPROPRIATE TIME, it is the opinion of the OP Team that it would NOT be possible to finish the magnet tests by Christmas 2006, or, drastic corrective measures would have to be taken in:

(a) totally reducing the magnetic Measurements,

(b) reducing the no. of training quenches  and so forth as well as that

(c) the logistics issues are solved in the manner done for Dipoles (handling by ICS).

All the above is of course based on present working conditions and not counting the yet unknowns of summer months. Cluster C, B, & D MUST be used EXCLUSIVELY FOR ALL SSS & SSSS  Testing from 1-June-06

The TABLE BELOW SHOWS THE OUTSTANDING 66 Special SSS’s and whether they are ICS or non-ICS treated ; Pink background are destined for Magnetic Measurements using Shafts & SSW, normally on D1 Bench while the 2 beige background (671,679) are supposed to be measured using the special Chaconsa scanner on bench D2. The 4 magnets in 500-series needing magnetic measurements would use only SSW & hence could also be put on B1 bench in this projection.

The Output in 2006 so far from dedicated Special SSS modified D Cluster used for Magnetic Measurements ( Chaconsa, Shafts, SSW) [ Feb-May 2006 = 4 months, 7  SSSS were tested on D1 bench, 6 with MM ;  17 on D2 without MM]