Vc/17-May-04

### Week21 starting 17 May 04

### SM18 Operation Meeting (Tuesdays)

Bench status  and tests for now & next few days :

| Bench | Name | Situation Mon 17/5 afternoon | Temp |
| --- | --- | --- | --- |
| TBA1 | MBAR3061 | Prep 2.2 IAP @ warm LF | 1.9 K |
| TBA2 | MBBL3117 | PT 1 IAP @ cold | 4.4 K |
| TBB1 | MBBL1104 | ICS 2 Connect Magnet (ICS) | 300 K |
| TBB2 | MBAL1071 | PT 12 Warm Up | Warming |
| TBC1 | MBBL1116 | New Magnet arrived | 300 K |
| TBC2 | SSS21 | PT 5.2 1.5 KA Quench HF | 1.9 K |
| TBD1 | MBBL2076 | PT 6.5 Training 5 | 1.9 K |
| TBD2 | MBBL2062 | ICS 1 WP04 HV Test Warm | 300 K |
| TBE1 | MBBL1112 | ICS 4 Final connection | 300 K |
| TBE2 | MBBL1113 | PT 6.7 Training 7 | 1.9 K |
| TBF1 | MBBL3151 | ICS 1 WP04 HV Test Warm | 300 K |
| TBF2 | MBAL3160 | PT 6.1 Training 1 |  |

Test Coordinator this week: Pierre ; MTM support on call  Federico:  (16-3602).

7 Dipoles  Disconnected after tests last week    ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- D2 Cryo Repair Last week of faulty Valve

A2  commissioning   & re-test     3117

A1         “                   &   re-test    3061

- D1 & D2  issues  ( Jurek)

- SSS work :        To Do list on Board+ GREY FILE IN SMCR

- General Problems last week :

| Date | Bench/ magnet | Problem | Cause | Solution |
| --- | --- | --- | --- | --- |
| Fri 14th aft | B1 (2039) | Power supply pblm for T-coil | Poor Config. | Giorgio fixed it |
| Fri 14th May night | D2 (2078) | Training quench at 7969A & down to ZERO without any reason | TEMA error like before ??? | quench ignored, training continued normally |
| Sat 15th May | C1 (3504) | Last HV cold test incomplete, discovered when magnet was already warming up (~40 K) | Human error – check with Khare? | Magnet cooled back down to 4.2, HV test completed |
| Sat 15th night | D Cluster | No label tags on Dipole leads at CFB level |  | Giorgio informed Mon.17th May |
| Sun 16th May | E2 (1113) | AQA timing faults on 1.5kA quenches | Slow quench development, most of signal lost due to insufficient 3s pre-trigger length | Quench repeated, acquisition worked successfully |
| Sun 16th May | E2 (1113) | Training quench at ~11kA | Unexplained V-clamp quench Cryo OK signal active | Quench ignored, training continued normally |
| Sat-Sun | All | TV status display crashed | Network/PC problems on Jerome’s DB ? | Pending |
| Sat-Sun | All | Water interlock on D-E cluster, no more than 2 Converters active (Flo) | Human error ? | Richard switched on all valves in the correct order |