vc/12-Jul-05

### Week 28  starting 11 July 05

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday  11 July 05 @: 7/11/2005 4:45:19 PM

| 3 | A1 | MBBR3365 | PT 12 Warm Up | 187.62 |
| --- | --- | --- | --- | --- |
| 8 | A2 | MBAR3306 | ICS 4 Final connection | 297.86 |
| 11 | B1 | SSS174 | Prep 5 Cool Down | 296.7 |
| 4 | B2 | SSS204 | Prep 3 CDW1 HV | 298.04 |
| 2 | C1 | MBAL1245 | Prep 0 Scan Bench | 296.88 |
| 10 | C2 | MBBL3156 | Prep 5 Cool Down | 242.66 |
| 7 | D1 |  |  | 297.32 |
| 12 | D2 | SSS641 | Finished Ready to go Final scan | 297.41 |
| 1 | E1 | MBBR3292 | Prep 0 Scan Bench | 298.04 |
| 5 | E2 | MBAL1244 | PT 5.1 1.5 KA Quench LF | 2.08 HV |
| 6 | F1 | MBAL3114 | Prep 5 Cool Down | 4.58 HV |
| 9 | F2 | MBAR3349 | ICS 4 Final connection | 296.43 |

Coordinator this week: John, Stephane +Marco;MTM support 16-3602

16 complete Magnet Tests cycles   (no ROBTC this week )

12  dipoles( 2 with MM )+ 3  SSS( 0  with MM) +  1 SSSS

Disconnected or ROBTC after tests last week ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- General Points  :

WEEKEND ISSUES :

  - Problems on B2 leak & labelling  : done 3 times ?

  - Not enough magnets or rather people to mount MRB’s from ICS

- AOB

## Tests

| Magnets under Test from 03-07-2005 to 09-07-2005 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |  |  |
| 1 | TBA1 | MBBL3095 |  |  | 02-07-2005 | 42 h. | 25 h. | 31 h. | 15 h. | 13 h. | 08-07-2005 | 126 h. | Stripping |  |  |
| 2 | TBA2 | MBAL2193 |  |  | 30-06-2005 | 0 h. | 24 h. | 12 h. | 14 h. | 24 h. | 03-07-2005 | 74 h. | Stripping |  |  |
| 3 | TBA2 | MBAR3372 |  |  | 03-07-2005 | 36 h. | 33 h. | 25 h. | 26 h. | 10 h. | 09-07-2005 | 130 h. | Stripping |  |  |
| 4 | TBB1 | SSS148 |  |  | 30-06-2005 | 37 h. | 16 h. | 15 h. | 8 h. | 38 h. | 05-07-2005 | 114 h. | Stripping |  |  |
| 5 | TBB1 | SSS282 |  |  | 05-07-2005 | 45 h. | 20 h. | 21 h. | 6 h. | 13 h. | 09-07-2005 | 105 h. | Stripping |  |  |
| 6 | TBB2 | SSS205 |  |  | 02-07-2005 | 30 h. | 14 h. | 26 h. | 26 h. | 18 h. | 07-07-2005 | 114 h. | Stripping |  |  |
| 7 | TBC1 | MBBR3314 |  |  | 02-07-2005 | 30 h. | 23 h. | 18 h. | 14 h. | 14 h. | 06-07-2005 | 99 h. | Stripping |  |  |
| 8 | TBC2 | MBAR3302 |  |  | 29-06-2005 | 32 h. | 33 h. | 18 h. | 17 h. | 29 h. | 05-07-2005 | 129 h. | Stripping |  |  |
| 9 | TBC2 | MBBR3366 |  |  | 05-07-2005 | 36 h. | 23 h. | 18 h. | 19 h. | 10 h. | 09-07-2005 | 106 h. | Stripping |  |  |
| 10 | TBD2 | SSS640 |  |  | 29-06-2005 | 44 h. | 16 h. | 43 h. | 37 h. | 47 h. | 06-07-2005 | 187 h. | Stand By |  |  |
| 11 | TBE1 | MBBR3273 |  |  | 01-07-2005 | 23 h. | 21 h. | 14 h. | 13 h. | 20 h. | 05-07-2005 | 91 h. | Stripping |  |  |
| 12 | TBE2 | MBBL2161 |  |  | 28-06-2005 | 51 h. | 28 h. | 17 h. | 18 h. | 20 h. | 04-07-2005 | 134 h. | Stripping |  |  |
| 13 | TBE2 | MBBR3359 |  |  | 04-07-2005 | 53 h. | 22 h. | 16 h. | 15 h. | 14 h. | 09-07-2005 | 120 h. | Stripping |  |  |
| 14 | TBF1 | MBAL2051 |  |  | 03-07-2005 | 33 h. | 23 h. | 36 h. | 19 h. | 13 h. | 09-07-2005 | 124 h. | Stand By |  |  |
| 15 | TBF1 | MBBR3308 |  |  | 29-06-2005 | 30 h. | 27 h. | 19 h. | 15 h. | 10 h. | 03-07-2005 | 101 h. | Stripping |  |  |
| 16 | TBF2 | MBAR3321 |  |  | 30-06-2005 | 29 h. | 25 h. | 35 h. | 15 h. | 9 h. | 05-07-2005 | 113 h. | Stripping |  |  |

### Quench Information

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBBL3095 | 11360 A. (D1_U_S01) | 12569 A. (D1_L_S01) | 12782 A. (D2-L-S01) |  | - | - | - | - | - | - | - | - | - |
| 2 | MBAL2193 | 12076.7 A. (D1_L) | 12150 A. (D2_U) |  | - | - | - | - | - | - | - | - | - | - |
| 3 | MBAR3372 | 9464.7 A. (D1-U) | 11606.1 A. (D1-U) | 11870 A. (D1-L) | 11986 A. (D2-L) | 12536 A. (D2-U) | 12850 A. | - | - | - | - | - | - | - |
| 4 | SSS148 | 11803.9 A. (QE_12) | 12402.7 A. (QE-12) | 12583.7 A. (QE_12) |  | - | - | - | - | - | - | - | - | - |
| 5 | SSS282 | 12020 A. (QE-12) | 12579 A. (QE-34) | 12747 A. (QE-12) |  | - | - | - | - | - | - | - | - | - |
| 6 | SSS205 | 11749 A. (QE_34) | 12409 A. (QE_12) | 12574 A. (QI_34) |  | - | - | - | - | - | - | - | - | - |
| 7 | MBBR3314 | 11287 A. (D1_U) | 12365 A. (D2_L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 8 | MBAR3302 | 12288.1 A. (D1_U) | 12504.7 A. (D2_U) | 12750.6 A. (D1-L) |  | - | - | - | - | - | - | - | - | - |
| 9 | MBBR3366 | 11758 A. (D2_U) | 12650 A. (D1-U) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 10 | SSS640 | 4807 A. (MQ_Ex_34) | 5377 A. (MQ_In_34) | 5817 A. (MQ_In_34) | 5820 A. | - | - | - | - | - | - | - | - | - |
| 11 | MBBR3273 | 11881.8 A. (D2_L) | 12859 A. | - | - | - | - | - | - | - | - | - | - | - |
| 12 | MBBL2161 | 11115.9 A. (D2-L) | 11781.6 A. (D2_U) | 12392 A. (D1-L) | 12507.5 A. (D1_U) |  | - | - | - | - | - | - | - | - |
| 13 | MBBR3359 | 11193.1 A. (D1_L) | 11077 A. (D1-U) | 12860 A. (D1-U) |  | - | - | - | - | - | - | - | - | - |
| 14 | MBAL2051 | 10888 A. (D2-L) | 11952 A. (D1-L) | 12223 A. (D1-U) | 12364 A. (D1-U) | 12653 A. (D1-U) | 12659 A. (D1-U) | 12664 A. (D1-U) | 12669 A. (D1-U) | 12671 A. (D1_U) |  | - | - | - |
| 15 | MBBR3308 | 1177 A. (D1-L) | 12236.5 A. (D1-L) | 12817 A. (D2_U) |  | - | - | - | - | - | - | - | - | - |
| 16 | MBAR3321 | 12125 A. (D2-U-S01) | 12525 A. (D1-L-S01) | 12738 A. (D2-L-S01) |  | - | - | - | - | - | - | - | - | - |

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday _05_N | TBD2 | after wire installation problem with motor control in y-axis for table A | MTM |  | Guy checked and found that the config-files were lost. He re-launched the scripts, made some tests and then OK. |
| Tuesday _05_N | TBE1 | One of the voltage tap wires has broken too far inside the CFB to be repaired. ICS will carry on connecting. | MTM |  | Proceed as is. |
| Tuesday _05_N | TBD1 | ACR team indicated an alarm on the temperature of the anti-cryostat short in aperture 2 (4.7 K). The history plot shows that it gradually decreased in temperature | MTM |  | Investigation by F.Flamand and J.L Ducret. Nothing strange found. Measurements the day after . Temperature became normal (17 C). |
| Wednesday _06_M | TBA1 | MM2 could not be launched from TEMA. | MTM |  | Giorgio and Maryline investigated. Config file not correct in TEMA. |
| Wednesday _06_M | TBF | Variac for adjusting the Voltage for minimum energy found to work badly (rotation 1/4 turn only). | MTM |  | Guy informed. Check on progress. |
| Wednesday _06_A | TBB1 | SSS282: ICS was asked to check the corrector circuit connection. | ICS |  | ? |
| Thursday _07_M | TBD1 | 4th chassis of potaim cards to be changed. | AB/CO |  | Guy contacted. |
| Thursday_07_A | TBF1 | MB2051: Quench at 4.4 K. Regulation problems for the two quenches. Difficulty to have the 4.4 K cryo OK. Process problem or stability problem? Results not conform to expectation (9000 A for Iquench) | ACR |  | Process not automatised anymore. To check in another magnet. |
| Thursday _07_A | TBA2 | Communication problem between server and PLC | AB/CO? |  |  |
| Thursday _07_N Friday _08_A | TBB2 | LF acquisition was not getting armed as some triggers existing, while launching prep 2.2c Again some triggers | ICS |  | ICS re-opened the M3 line and checked the connection of the EF clamp. A wire was found broken. SSS with new configuration of connection. But not in the list given to OP team. ICS had managed to connect it using the old schema?? |
| Thursday _07_N | TBB2 | HF window is not getting displayed in the local server during the IAP at cold. | AB/CO | hf | Rebooting the sun test could be carried out in normal conditions |
| Thursday _07_N | TBC1 | Lf 1.5 kA quench: flat signal for D1-D2. Cable for this potaim card disconnected. Not reconnected after the offsets adjustments of the potaim cards | MTM |  | Cable re-connected and test program went on. Lf quench checked by Stephane Friday. OK given for warming up. |
| Saturday _09_A | TBC1 | MBB2197: After each quench (training 2) the vacuum degrades (10-4 mbar) not seen at warm. |  |  | Test stop: investigation by ACR team if it come from magnet or CFB. |
| Saturday _09_A | TBD2 | Disconnection of the SSS641 by ICS with rotary switch put in D2! | MTM |  | Not allowed for safety reasons. Switch put in CC. |
| Saturday _09_A | TBA2 | MB3349 (with MM) put on TBA2 and not on TBF2 as foreseen. | ICS |  | Rocla and ICS informed. TC also contacted. |
| Saturday_09_N | TBC2 TBB2 | Scan cannot be performed with the MOBIC (MB3156). Same problem for SSS on TBB2 | MTM |  | Magnet name entered manually. Guy came and found that the battery had a problem: action on underway. |
| Sunday_10_M | TBB2 | Leak on M2 line of SSS204 | ICS |  | Joint changed but leak remained. M2 line and M3 line inverted. Leak in M3 line! Magnet to be re-connected. |
| Sunday_10_A | TBA1 | During MMP2 LHC cycle, the rotation goes to the end stop for aperture 2 | MTM |  | The TRU cover is touching the flat cables. Guy advised to proceed. |
| Sunday_10_N | TBF2 | No communication between PLCSE and server. | AB/CO |  | Exit from the server reset the PLCSE. |
| Monday_11_M | TBA | Hf DAQ could not be armed. | AB/CO |  |  |
| Monday_11_M | TBE2 | Trigger in Potaim card D2_L because of a significant offset. | MTM |  | Maryline informed. Maryline changed the card. |