### VC- /Week 48 starting   04Dec06

### SM18 Operation Meeting (Tuesdays) 05 dec  06

Bench status  on sunday 3-Dec-2006 at   12/3/2006 9:49:24 PM

| 12 | A1 | MBBR2363 | Prep 5 Cool Down | 295.89 |
| --- | --- | --- | --- | --- |
| 8 | A2 | MBAR2404 | ICS 3 Traveller after warm test | 295.62 |
| 11 | B1 |  |  | 294.64 |
| 3 | B2 |  |  | 295.8 |
| 2 | C1 | SSS373 | PT 9 CDAP HV | 234.95 |
| 7 | C2 | SSS365 | Prep 5 Cool Down | 295 |
| 1 | D1 | SSS622 | PT10.1 Provoked Quench 1/2 HF 11850 | 237.67 |
| 6 | D2 | SSS694 | Prep 5 Cool Down | 87.77 |
| 9 | E1 | MBAR2410 | Prep 5 Cool Down | 93.26 |
| 4 | E2 | MBAR2409 | Prep 5 Cool Down | 87.2 |
| 5 | F1 | MBAR1414 | Prep 5 Cool Down | 294.91 |
| 10 | F2 | MBAR2413 | Prep 3 CDW1 HV | 295.18 |

CONFIG :  D 6 - AS 2 -  IRSSS 4 ;

Supervisor:  arjan ;        Eq support 16-3602 :

09 Magnet Tests completed ( 5 Magnet Stripped ) ;

5 Dipoles tests + 1406 not tested HV fail at beginning	( 3 signed stripping)

2 Arc-SSS (  363 )

1 500-series ( 522  )

1  600-series [ 675 (287 hrs)]

Situation from Cryogenics:  J-P Lamboy .   PROBLEMS since last  Fri (no Helium)

All OP shifts cancelled since last sat morning...

General Points:

- Situation SSSS  :D1 & D2 issues J Halik

- A.O.B

| Magnets under Test from 26-11-2006 to 02-12-2006 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |  |  |
| 1 | TBA2 | MBAR2412 |  |  | 24-11-2006 | 53 h. | 22 h. | 19 h. | 18 h. | 12 h. | 02-12-2006 | 124 h. | Stripping |  |  |
| 2 | TBB2 | SSS522 |  |  | 22-11-2006 | 57 h. | 15 h. | 19 h. | 10 h. | 20 h. | 01-12-2006 | 121 h. | Stripping |  |  |
| 3 | TBC1 | SSS297 |  |  | 22-11-2006 | 29 h. | 12 h. | 32 h. | 9 h. | 8 h. | 26-11-2006 | 90 h. | Stripping |  |  |
| 4 | TBC2 | SSS052 |  |  | 23-11-2006 | 36 h. | 20 h. | 44 h. | 7 h. | 17 h. | 29-11-2006 | 124 h. | Stand By |  |  |
| 5 | TBD2 | SSS675 |  |  | 15-11-2006 | 47 h. | 58 h. | 127 h. | 11 h. | 44 h. | 27-11-2006 | 287 h. | Stripping |  |  |
| 6 | TBE1 | MBAR2410 |  |  | 25-11-2006 | 45 h. | 20 h. | 53 h. | - | - | 01-12-2006 | 118 h. | Not Found or Thermal cycle |  |  |
| 7 | TBE2 | MBAL2282 |  |  | 23-11-2006 | 0 h. | 27 h. | 24 h. | 17 h. | 14 h. | 28-11-2006 | 82 h. | Stand By |  |  |
| 8 | TBF1 | MBBR1371 |  |  | 22-11-2006 | 45 h. | 22 h. | 15 h. | 15 h. | 33 h. | 30-11-2006 | 130 h. | Stand By |  |  |
| 9 | TBF2 | MBBR1366 |  |  | 22-11-2006 | 83 h. | 33 h. | 15 h. | 15 h. | 22 h. | 30-11-2006 | 168 h. | Stripping |  |  |
| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| 1 | MBAR2412 | 11397.7 A. (D1_U) | 12495 A. (D2_L) | 0 A. (No Data) | 0 A. (No Data) | 12852 A. | - | - | - | - | - | - | - | - |
| 2 | SSS522 | 10901 A. (QI-12) | 11787.9 A. (QE_34) | 12349.4 A. (QI_34) | 12492.8 A. (QE_34) |  | - | - | - | - | - | - | - | - |
| 3 | SSS297 | 11388.5 A. (QI-12) | 12588.1 A. (QI_12) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 4 | SSS052 | 12849.7 A. (QE_34) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 5 | SSS675 | 5355 A. (E_MQY_1) | 5756.7 A. (IN-MQY-2) | 5820 A. | - | - | - | - | - | - | - | - | - | - |
| 6 | MBAR2410 | 12344.5 A. (D2_U) | 12772.2 A. (D2_U) | 11750 A. (D2_U) | 11950.2 A. (D2_U) | 12264.6 A. (D2_U) | 12554.2 A. (D2_U) | 12252.1 A. (D2_U) | 12531.7 A. (D2_U) | 12348.9 A. (D2_U) |  | - | - | - |
| 7 | MBAL2282 | 12850 A. | - | - | - | - | - | - | - | - | - | - | - | - |
| 8 | MBBR1371 | 11136.4 A. (D2_U) | 12498.2 A. (D1_U) | 12558.1 A. (D1_L) |  | - | - | - | - | - | - | - | - | - |
| 9 | MBBR1366 | 12145.4 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_28_A | TBC1 | SSS373: EF correctors powering: the current ramping up and down cannot be displayed. It is ok on the power converter application, but not on lf web | MTM |  | Giorgio contacted. Giorgio found that the two banana cables (current reading) were disconnected on the Power converter itself (probably by AB-PO during calibration). Restore the two cables and it was OK. Test repeated. |
| Tuesday_28_A | TBD1 | SSS694 HWREC access problem: Name disappears from TEMA. Error message coming. Impossible to do set test type and reset: test unknown | MTM | HWREC | Giorgio came. This type of S4 (6xMQTK) will not be recognized. Test will be performed with HWREC off. |
| Tuesday_28_N | TBD1 | SSS622: The PLCSE had no communication with TEMA There was still the problem of HWREC: Consequence of the installation of the SSS694 has been installed in the afternoon (D2). | MTM |  | Giorgio restarted the PLCSE and the server. HWREC switched off and MM3 can be launched on SSS622. |
| Tuesday_28_N | TBE2 | MBAR2409: HV Test WP04 not found hence further testing stopped. | ICS |  | Informed to ICS. According to ICS magnet is connected now. |
| Wednesday_29_N Thursday_30_N | TBE1 TBD1 | Liquefactor problem : Temperature stability affected. | ACR |  | No quench is allowed till the OK of cryo tema: Test on MB2410 postponed, MM on SSS622 stopped. No MM and quench during Thursday night |
| Friday_01_M | All | Liquefactor blocked because of impurities in the walves box. No helium available. Box that should be partially warmed. | ACR |  | Magnets are warming up. Testd at cold and cool-down below 80 K stopped. |
| Friday_01_N | TBA1 | MB2363: Temperature of anticryostat too low. | MTM |  | Cables not connected properly. Corrected. |
| Saturday, Sunday | All | No liquid helium. | ACR |  |  |
| Monday_04_M | All | Power cut. Restart of the test during the day. | TS |  |  |