### VC- /Week 49 starting   11Dec06

### SM18 Operation Meeting (Tuesdays) 12 dec  06

Bench status  on monday 11-Dec-2006 at  12/11/2006 9:39:04 AM

| 2 | A1 | MBBR2363 | PT 13.2 Resist. Meas. | 296.34 |
| --- | --- | --- | --- | --- |
| 7 | A2 | MBAR2416 | ICS 4 Final connection | 295.98 |
| 12 | B1 | SSS519 | Prep 0 Scan Bench | 296.34 |
| 9 | B2 | SSS525 | PT5.4: Powering Corrector EF | 1.90 |
| 3 | C1 | SSS368 | PT 13.2 Resist. Meas. | 295.89 |
| 11 | C2 | SSS365 | PT 14 Magnet MAPS | 295.54 |
| 8 | D1 | SSS674 | PT 6.12 Training 12 | 2.35 |
| 6 | D2 | SSS694 | PT 13.2 Resist. Meas. | 296.88 |
| 10 | E1 | MBAR2415 | PT 13.2 Resist. Meas. | 298.04 |
| 4 | E2 | MBBR2417 | ICS 4 Final connection | 296.25 |
| 5 | F1 | MBBR1345 | Prep 2.3 Res. Meas. CDW1 | 295.18 |
| 1 | F2 | MBAR2413 | PT 14 Magnet MAPS | 295.36 |

CONFIG :  D 6 - AS 2 -  IRSSS 4 ;

Supervisor:  stephane ;        Eq support 16-3602 :

RECORD OF WORST WEEK IN HISTORY OF SM18 since July 2004 ( all 12 Benches operation)

674 : long no of quenches & sp tests ?

Can we not attempt to finish 6 series this year ? & maximum of 5 series possible ?

05 Magnet Tests completed ( 4 Magnet Stripped ) ;

3 Dipoles tests + 1406 not tested HV fail at beginning	( 3 signed stripping)

1 Arc-SSS (  373 )

0 500-series (  )

1  600-series [ 622(325 hrs)]

Situation from Cryogenics:  J-P Lamboy .

General Points:

- Situation SSSS  :D1 & D2 issues J Halik

- A.O.B

TERMINATION TICK OFF COUNTER

( SPECIAL & NORMAL SSS )

| MAGNET | ARRIVAL | DEPARTURE | Tick if Done |
| --- | --- | --- | --- |
| 525 | 05/12/2006 |  |  |
| 509 |  |  |  |
| 523 |  |  |  |
| 516 |  |  |  |
| 519 | 08/12/2006 |  |  |
| 529 |  |  |  |
| 530 |  |  |  |
| 531 |  |  |  |
| 669 |  |  |  |
| 695 | 11/12/2006 |  |  |
| 370 |  |  |  |
| 361 |  |  |  |
| 099 |  |  |  |
| 374 |  |  |  |
| 356 |  |  |  |

Updated : Tuesday, December 12, 2006

## Tests

| Magnets under Test from 03-12-2006 to 09-12-2006 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |  |  |
| 1 | TBA2 | MBAR2404 |  |  | 02-12-2006 | 49 h. | 51 h. | 25 h. | 24 h. | 16 h. | 09-12-2006 | 165 h. | Stripping |  |  |
| 2 | TBC1 | SSS373 |  |  | 26-11-2006 | 33 h. | 12 h. | 59 h. | 90 h. | 10 h. | 05-12-2006 | 204 h. | Stripping |  |  |
| 3 | TBD1 | SSS622 |  |  | 22-11-2006 | 67 h. | 15 h. | 225 h. | 9 h. | 9 h. | 05-12-2006 | 325 h. | Stand By |  |  |
| 4 | TBE1 | MBAR2410 |  |  | 01-12-2006 | 0 h. | 81 h. | 13 h. | 20 h. | 11 h. | 07-12-2006 | 125 h. | Stripping |  |  |
| 5 | TBE2 | MBAR2409 |  |  | 28-11-2006 | 45 h. | 127 h. | 34 h. | 26 h. | 16 h. | 09-12-2006 | 248 h. | Stripping |  |  |

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBAR2404 | 10642.6 A. (D2-U) | 12323.5 A. (D2-L) | 12784.9 A. (D1_U) |  | - | - | - | - | - | - | - | - | - |
| 2 | SSS373 | 10888.8 A. (QE-34) | 11858.8 A. (QE_34) | 11831 A. (QE_34) | 12159 A. (QE_12) | 12439 A. (QE_34) | 12570.7 A. (QE_34) | 12599.8 A. (QE_34) | 12688 A. (QI_34) | 12819.2 A. (QI_34) |  | - | - | - |
| 3 | SSS622 | 3211.9 A. (Ext_34) | 3531.6 A. (IntMQY34) | 3633.1 A. (IntMQY12) | 3715.2 A. (Int_12) | 3755.4 A. (Ext_34) | 3785.1 A. (Ext_12) | 3697.5 A. (Int_12) | 3812.7 A. (Ext_MQ34) | 3854.4 A. (MQY_E_12) | 3896.9 A. (MQY_I_12) | 3900 A. | - | - |
| 4 | MBAR2410 | 12559.2 A. (D2_L) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 5 | MBAR2409 | 10290.5 A. (D2_L) | 10754.8 A. (D1_L) | 11979.3 A. (D1-L) | 12423.7 A. (D1_U) | 12588.5 A. (D2-L) | 11925.7 A. (D2_L) | 12731.2 A. (D1_U) | 12850 A. | - | - | - | - | - |

Back to Homepage | For print (Test/Quench/Graph)| For print (Waiting time\Disconnect time\Graph)

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_5_N | TBE2 | MBAR2409: During provoked quench at 1/2 LF no Quench detected. Test repeated given same result. | MTM | lf | Salem contacted. He found that the quench was symmetrical and suggested to continue. |
| Tuesday_5_N | TBC2 | SSS365: No file was generated when corrector GH quenched at 56A | AB/CO |  | Stéphane asked Salem to check the powering up to ultimate. OK. |
| Wednesday_6_M | TBA1 | MB2363: Problem of power converter so not able to launch power test (PT4). | MTM |  | Salem checked and found Ext. Switch on the top of power converter was off due to Monday morning power cut so he resumed the same. |
| Wednesday_6_A | TBA1 | MB2363: MM1 was not successful in aperture 1. RMS (~4%) and angle Difference errors appeared on Ap1. | MTM |  | Salem and Patrick replaced the motor coupling which cured the RMS problem. Further investigation will continue tomorrow concerning the end-stop. (Training will continue on A1 then A2 will be tested before measuring A1) |
| Thursday_7_M | TBC1 | SSS368: During IAP at warm permanent trigger on V clamp and V supra-internal. | MTM |  | Salem contacted. |
| Thursday_7_N | TBF2 | MB2413: HV insulation test @ cold final, the step "Dipole-All QH vs ground" failed @ 3050V, but other test pass "Dipole vs ground" and "All QH vs ground" | MTM |  | Check by Salem: The failed sequence was re-run and OK to warm up. |
| Thursday_7_N | TBE1 | MB2415: C10 connector is loose and clips are missing. But IAP at warm tests are conducted. In Prep2.1 V-Taps error was found in V_Tanode and Vt cathode (-1.01V instead of +0.5 V). After connecting Left connector in D20, the V-Taps values are O.K. But it seems the Diode polarity is reversed. | MTM |  | Salem contacted. He checked and found the connection to the DAQ was reversed, he normalised the same and asked to repeat the test. |
| Friday_08_M | TBE1 | MB2415: IAP to be repeated but could not be launched. Cryo error Mag300.x1 and Mag300air.x1 | ACR |  |  |
| Friday_08_M | TBE1 | MB2415: Prep 2.1 repeated and again same problem found for Voltage Taps. OP team did resistance measurement and found not ok. | MTM |  | IFS box opened and there was inversion of leads corrected |
| Saturday_09_N | TBB2 | SSS525: Cryo OK in HV phase lost. | ACR |  |  |
| Saturday_09_N | TBA2 | MB2416: Unable to launch Prep 2.1, due to communication errors displayed in TEMA. Error receiving INFO from UDP socket. Problem persists even after resetting and restarting all applications, including PLC and crates. The application that is blocking is hf. | AB/CO | hf | Salem called. He came and solved the problem by resetting sun station 31 and 44. |
| Sunday_10_M | TBA2 | MB2416: 2 alerts for HF quench Heaters discharge (QH2-3 Vinit <810V -- QH3 E<2000) during Prep 2.2 | MTM |  | Test redone then OK. |