### VC- /Week 3 starting   15Jan07

### SM18 Operation Meeting (Tuesdays) 16 Jan  07

HOW THE SITUATION WAS AT END 2006 and  at START UP ON 8 Jan 2007

| 2 | A1 | MBAR2411 | PT 13.2 Resist. Meas. | 295.18 |
| --- | --- | --- | --- | --- |
| 8 | A2 | MBAR2268 | ICS 1 WP04 HV Test Warm | 294.19 |
| 9 | B1 | SSS519 | PT 14 Magnet MAPS | 294.28 |
| 1 | B2 | SSS516 | ICS 5 Traveller Last | 295 |
| 7 | C1 | SSS099 | Prep 5 Cool Down | 161.17 |
| 5 | C2 |  |  | 294.55 |
| 3 | D1 | SSS669 | PT 13.2 Resist. Meas. | 294.55 |
| 10 | D2 | SSS509 | Prep 0 Scan Bench | 295 |
| 4 | E1 | MBAR2402 | PT 13.2 Resist. Meas. | 295.44 |
| 6 | E2 | MBBR2394 | Prep 5 Cool Down | 274.22 |
| 11 | F1 | MBBL2197 | Prep 2.3 Res. Meas. CDW1 | 294.01 |
| 12 | F2 | MBAR2407 | ICS 4 Final connection | 293.74 |

1/8/2007 4:56:34 PM   Tempr. from TBSM18 site

E2 & C1 were leak checked already before Xmas shutdown

### VC- /Week 3 starting   15Jan07

### SM18 Operation Meeting (Tuesdays) 16 Jan  07

Bench status  on monday 15-Jan-2007 at   1/15/2007 2:54:50 PM

| 7 | A1 | MBBR2384 | Prep 5 Cool Down | 173.84 |
| --- | --- | --- | --- | --- |
| 5 | A2 | MBAR2268 | PTE Min. NRJ 3KA Diode Test | 13.88 |
| 8 | B1 |  |  | 295.62 |
| 9 | B2 |  |  | 296.34 |
| 1 | C1 | SSS099 | PT 13.2 Resist. Meas. | 295.18 |
| 10 | C2 |  |  | 295.62 |
| 11 | D1 | SSS523 | ICS 3 Traveller after warm test | 295.8 |
| 6 | D2 | SSS509 | PT 6.2 Training 2 | 1.90 |
| 12 | E1 | MBAR2414 | ICS 1 WP04 HV Test Warm | 296.52 |
| 3 | E2 | MBBR2394 | PT 13.2 Resist. Meas. | 296.34 |
| 4 | F1 | MBBL2197 | PT 13.2 Resist. Meas. | 294.64 |
| 2 | F2 | MBAR2407 | ICS 6 Disconnect Magnet WP07 | 295.36 |

CONFIG :  D 6 - AS 2 -  IRSSS 4 ;

Supervisor:  Arjan ;        Eq support 16-3602 :

4 ( + 2 ) Magnet Tests completed ( 1 Magnet Stripped ) ;

2 Dipoles tests

1 Arc-SSS (  370 )

0 500-series ( )

1  600-series [ 669 – last one : was completed in Dec]

+ B cluster magnets 516, 519  already done  were NOT removed till Monday 15th

SSS099 + 2394 were tested but s99 had ROBTX & 2394 had HV problems at CDBP

Situation from Cryogenics:  J-P Lamboy .

General Points:

Work Hours : ICS & Cryo Teams   ( Eric + Kevin)

Control Room Lock up  - pin code  ( Eric)

2 -person Rule

- Situation  all SSS  : J Halik :

- Situation Cryo ( J-P Lamboy) & Feb working

- A.O.B

## Tests

| Magnets under Test from 07-01-2007 to 13-01-2007 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |  |  |
| 1 | TBA1 | MBAR2411 |  |  | 13-12-2006 | 61 h. | 30 h. | 100 h. | 8 h. | 470 h. | 10-01-2007 | 669 h. | Stripping |  |  |
| 2 | TBC2 | SSS370 |  |  | 17-12-2006 | 0 h. | 29 h. | 10 h. | 9 h. | 52 h. | 08-01-2007 | 100 h. | Stripping |  |  |
| 3 | TBD1 | SSS669 |  |  | 14-12-2006 | 37 h. | 26 h. | 53 h. | 10 h. | 495 h. | 09-01-2007 | 621 h. | Stand By |  |  |
| 4 | TBE1 | MBAR2402 |  |  | 16-12-2006 | 42 h. | 21 h. | 15 h. | 17 h. | 552 h. | 12-01-2007 | 647 h. | Stand By |  |  |

### In addition, SSS099 tested twice ( ROBTC) ; 2394 had HV problems at cold & was warmed up

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBAR2411 | 10704.4 A. (D2_U) | 11688 A. (D1_U) | 12514.8 A. (D1_U) | 12520 A. (D1_L) |  | - | - | - | - | - | - | - | - |
| 2 | SSS370 | 11991.2 A. (QE_12) | 12190.4 A. (QE_12) |  | - | - | - | - | - | - | - | - | - | - |
| 3 | SSS669 | 3513 A. (Ext_MQML) | 3998.6 A. (Ext_MQML) | 4157 A. (Ext_MQM) | 4367.1 A. (Int_MQM) | 4355 A. (Ext_MQM) | 4447.4 A. (Int_MQML) | 4483.4 A. (E_MQM) | 4499 A. (I_MQM) | 4505 A. (I_MQML) | 4529.5 A. (Ex_MQML) | 4574.9 A. (Ex_MQML) | 4587.1 A. (Int_MQM) | 4602.8 A. (Ext_MQML) | 4638.5 A. (Int_Mqml) | 4650 A. |
| 4 | MBAR2402 | 12229.6 A. (D2_L) | 12615 A. (D2_U) | 12850 A. | - | - | - | - | - | - | - | - | - | - |  |  |

MTM TEAM  (6:00-22:00)

Shift Leader 		160060

OP1					160483

OP2					160077

Nick					160957

ICS TEAM (7:30-16:00)

ICS (Chef de banc)		162926

ROCLA					165059

JOSEPH ROMANELLO	164649

CRYO TEAM (6:00-22:00)

CRYO MOBILE		160354

EXPERT (OLD Equipment support) (Normal hours)

HV		Richard MOMPO	164157

MM		Guy DEFERNE	164284

IAP/HF/LF: 	Giorgio D’ANGELO 163793

Salem BOUCHENOUA 163557

ANTI-CRYOSTAT:Patrick Legrand1632

| 08/01/2007 | TO DO LIST for SHIFT |
| --- | --- |
|  |  | START MORNING SHIFT |
| SMS | 1 | New elogbook session. |
|  | 2 | KEY CLUSTER A,B,C,D,E,F present on electrical box. Then SM18CR key. |
|  | 3 | Mobile present Shift leader 160060, OP1:160077, OP2:160483 |
|  | 4 | Check priority and consigned on with board, then previous logbook session. |
|  | 5 | Check Any problem from cryo during night |
|  | X | Start test on bench (If still are ready) |
|  |  | END MORNING SHIFT |
| EMS | X | Test on bench (If still are going on). |
|  | 1 | Put a maximum of information in elogbook for next shift. |
|  | 2 | Pass information to next shift. |
|  |  | START AFTERNOON SHIFT |
| SAS | 1 | Received information from previous shift. |
|  | 2 | New elogbook session. |
|  | X | Test on bench (If still are going on). |
|  |  | END AFTERNOON SHIFT |
| EAS | X | STOP test on bench (If still are going on). |
|  | 1 | Put a maximum of information in elogbook for next shift. |
|  | 2 | KEY CLUSTER A,B,C,D,E,F present on electrical box. Then SM18CR key. |
|  | 3 | Mobile present Shift leader 160060, OP1:160077, OP2:160483 |
|  | 4 | Check clearty of priority and consigned on with board. |
|  | 5 | Request Cryo operator to close the SM18CR. And put Key in cupboard. |
|  |  | New elogbook session |
|  |  | Check Equipment |
|  |  | Test on bench |
|  |  | Information exchange with CRYO or Previous/Next Shift. |

TERMINATION COUNTER -2007

Remaining of the totally 1250 Dipoles cryostated  that still  need testing this year

| No | MAGNET | BENCH | ARRIVAL | DEPARTURE | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | 2407 | F2 | 19-12-2006 |  |  |
| 2 | 2268 | A2 | 21-12-2006 |  |  |
| 3 | 2384 | A1 | 10-01-2007 |  |  |
| 4 | 2394 | E2 | 16-12-2006 |  |  |
| 5 | 2326 (MM) |  |  |  |  |
| 6 | 2263 |  |  |  |  |
| 7 | 2267 (MM) |  |  |  |  |
| 8 | 2399(MM) |  |  |  |  |
| 9 | 2423 |  |  |  |  |
| 10 | 2424 |  |  |  |  |
| 11 | 2425 |  |  |  |  |
| 12 | 2426 |  |  |  |  |
| 13 | 2324 |  |  |  |  |
| 14 | 2551 |  |  |  |  |
| 15 | 2598 |  |  |  |  |
| 16 | 2739 |  |  |  |  |
| 17 | 2328 |  |  |  |  |
| 18 | 2790 |  |  |  |  |
| 19 | 2624 |  |  |  |  |
| 20 | 2414 | E1 | 12-12-2006 |  |  |
| 21 | 2408 |  |  |  |  |
| 22 | 2420 |  |  |  |  |
| 23 | 2419 |  |  |  |  |
| 24 | 2418 |  |  |  |  |
| 25 | 2326 |  |  |  |  |
| 26 | 1334 |  |  |  |  |

15 of  26 Dipoles for completion of Tunnel                            Updated : January 16, 2007

TERMINATION COUNTER -2007    [ ALL SSS ]

| 29 | SSS 509 |  | 10-01-2007 |  |  |
| --- | --- | --- | --- | --- | --- |
| 30 | SSS 523 |  | 10-01-2007 |  |  |
| 31 | SSS 516 |  | 15-12-2006 | 15-01-07 | Done |
| 32 | SSS 529 |  |  |  |  |
| 33 | SSS 530 |  |  |  |  |
| 34 | SSS 531 |  |  |  |  |
| 35 | SSS 370 |  | 12 DEC 06 17 Dec :ROBTC |  |  |
| 36 | SSS 361 |  |  |  |  |
| 37 | SSS 099 |  | 18/12/2006 |  |  |
| 38 | SSS 374 |  |  |  |  |
| 39 | SSS 356 |  |  |  |  |
| 40 | SSS 367 |  |  |  |  |
| 41 | SSS 369 |  |  |  |  |
| 42 | SSS 364 |  |  |  |  |

Updated : January 16, 2007

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_09_A | TBE2 | MB2394: HV test at cold failed dipole vs ground | MTM |  | Richard contacted. IFS box removed for investigation. Fault confirmed. Magnet warm up naturally and removed without test. |
| Tuesday_09_A | TBC1 | SSS099: Powering of corrector not possible: Power converter was not going to standby. | MTM |  | Giorgio contacted. He found the switch on wrong position (off position). |
| Tuesday_09_A | TBD2 | SSS509: During HV initial @ warm MQTL vs Ground failed. | MTM | HV | Richard investigated the problem: capacity limit in the software corrected. Solved. |
| Tuesday_09_A | TBA2 | MB2268: Leak in the magnet found by cryo team found during capillary leak test. | ICS |  | ICS team changed the join in the line E. |
| Monday_15_M | TBD2 | SSS509: Training 2 could not be launched: PLCSE blocked. | MTM |  | TEMA and Power Converter reset but still fault. Giorgio informed. He did the same manipulation three times and then OK. |