vc/18-Nov-03

### Week 47 starting 17 nov 03

### SM18 Operation SCHEDULE Meeting (Tuesdays)

Schedule for this week :

| BENCH | CURRENT MAGNET | STATUS Today(18/11/03) | Forward look, & Next Magnet |
| --- | --- | --- | --- |
| TBA1 | NOT Active |  | Bench de-activated – preparation for D bench “Park” here 2001 ( moved from D bench ) |
| TBA2 | 3022 | cold |  |
| TBC1 | 3027 | To warm up & disconnect | 1027 next ? |
| TBC2 | SSS04 | cold |  |
| TBE1 | 2027 | connection | Arrived yesterday |
| TBE2 | 2029 | connection | Arrived yesterday |
| TBF1 | 3059 | connection |  |
| TBF2 | 3034 | Cold tests |  |

In pipeline Next 1028

Test Coordinator this week:  Marco B;  MTM  Tech. on call:  (16-3602) : Guy D

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- Other General Issues

  - Care in Ohmic M’ments

  - Magnet arrivals & label + Notify Equip. Support

  - New OP staff arrivals ( 2 India, 3 AB-OP)

  - AOB

SnapShot of STATUS NOW(Tues 18/11 1700 hrs):

SM18 LHC Magnet Test Facility

| TBA1 | _ | _ |  |
| --- | --- | --- | --- |

| TBA2 | MBAR3022 | PT7.1 Minimum NRJ | 1.9 K |
| --- | --- | --- | --- |

| TBB1 | _ | _ |  |
| --- | --- | --- | --- |

| TBB2 | _ | _ |  |
| --- | --- | --- | --- |

| TBC1 | MBAR3027 | PT12 Warm Up | Warming |
| --- | --- | --- | --- |

| TBC2 | SSS004 | PT12 Warm Up | Warming |
| --- | --- | --- | --- |

| TBD1 | _ | _ |  |
| --- | --- | --- | --- |

| TBD2 | _ | _ |  |
| --- | --- | --- | --- |

| TBE1 | MBAR2027 | New Magnet arrived | 300 K |
| --- | --- | --- | --- |

| TBE2 | MBAR2029 | New Magnet arrived | 300 K |
| --- | --- | --- | --- |

| TBF1 | MBAL3059 | ICS 2 Traveller AFTER Bolting | 300 K |
| --- | --- | --- | --- |

| TBF2 | MBBR3034 | PT7.1 Training 1 | 1.9 K |
| --- | --- | --- | --- |

Problems of Last week

| Date | Problem | Type | Application/soft. | Action/advise |
| --- | --- | --- | --- | --- |
| Tuesday 11_N | TBE2: Tcoils problem Bridge needed IAP @ cold: error for D1_L-U (119 mV) | MTM |  | Federico solved the problem Difficult to make better. |
| Tuesday 11_N | TBE2: PLCSE OK lost during ramp to 1 kA Slow PA has to be repeated. | MTM |  |  |
| Wednesday 12_M | TBE2: Impossible to put current | AB/PO |  | Power converter not working . It has been changed, |
| Wednesday 12_M | TBE2: MM0: MUX problem during auto-test | MTM |  | GPIB interface cable damaged. |
| Wednesday 12_A | TBE2: Provoked quench LF Timing error (tfire~3s) | MTM | AQA |  |
| Thursday 13_A | TBF2: Anticryostat (long) coefficient not correct. D07 instead of D11/12 | MTM |  | Solved by Federico |
| Thursday 13_N | TBE2: Low charging rate of QH (LF) | MTM |  |  |
| Thursday 13_N | TBE1: Waiting for Cryo OK? | ACR |  | 2 h between 4.2 K and 1.9 K is foreseen (JP lamboy) |
| Friday 14_M | TBC1: IAP @ warm (prep) and HV test not done and magnet under pumping. | MTM/ICS/ACR |  | HV test done during the pumping as per instruction of test coordinator. Traveller not updated. |
| Friday 14_A | TBA2: Transfer file of data for HV not done although message: transfer successfully done | MTM | HV | Space problem. Need space for the files. |
| Friday 14_A | Liquefactor problem : no cooling | ACR |  |  |
| Friday 14_A | TBE1: IAP@cold QH not discharged. | ACR |  | Wait for cryo OK. |
| Saturday 15_A | TBF2: Impossible to cool down 3034 from 4.5 K to 1.9 K | ACR |  | Piquet cryo called. |
| Saturday 15_N | TBC1: Cryo problem with current leads. Tprobe not working | ACR |  | Solved by Bruno Sunday 16. |
| Saturday 15_N | TBF2: During selection of tests in local (IAP, MM0) Interconnection switch box off. Trigger sent. Discharge of the heaters. | MTM |  |  |
| Saturday 15_N | TBF2: MM0 auto test. Serial communication error for motor and amplifier. | MTM |  |  |
| Sunday16_M Sunday 16_A | TBF2: Power Converter problem. “Water fault”’ | MTM | AB/PO | Corrected Monday morning by AB/PO increasing the flow to 8 l/sec |
| Sunday16_M | TBE1: main rotary switch blocked, difficult to manipulate. Done by Federico and faulty signal (mechanical disalignment) | MTM |  |  |
| Sunday16_M | TBA2: A2 C anticryostat goving –3.5 C PLC art not heating. | ACR/MTM |  | Solved. |
| Sunday16_M | TBE1: Misunderstanding with ACR team for RRR measurements. | ACR/MTM |  | Repeated later. |
| Sunday16_A | TBC1: Slow PA abort. “lead Temp.A-X1’’ problem | ACR |  |  |
| Sunday16_N | TBC1: Min energy 3 kA : trigger in Vbus ext. Threshold in the card too low (1.16 V instead 1.6 V). | MTM |  | Corrected by Federico. Repeated then OK |
| Monday 17_M | TBC1: MM0 No meas. Current in Ap1. Cable used for TBC2. | MTM |  | Solved by Guy. |
| Monday 17_M | Computer T7 blocked. |  |  | PC support called. |
| Monday 17_A | TBA2: Provoked quench all HF Error in HF quench heater acquisition | MTM | AQA |  |
| Monday 17_A | TBC1; PConverter ; interlock water | AB/PO |  |  |