Vc/22-Nov-04

### Week48 starting 22 Nov 04

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday 22 Nov 04  ~11/22/2004 12:38:45 PM

LHC SM18 Magnet Test Facility

| 5 | A1 | MBBL3219 | Prep 5 Pumping + Cool Down | 90.2 |
| --- | --- | --- | --- | --- |
| 9 | A2 | MBAR3204 | ICS 6 Disconnect Magnet WP07 | 299.1 |
| 12 | B1 | SSS614 | ICS 5 Traveller Last | 295.6 |
| 1 | B2 | MBBL2043 | PTE 1 Minimum NRJ + RRR | 9.8 |
| 7 | C1 | MBAR3257 | PT 12 Warm Up | 79.5 |
| 4 | C2 | MBBL1168 | Prep 5 Pumping + Cool Down | 294.6 |
| 11 | D1 | SSS039 | CL-1 Call Transport | 295.1 |
| 2 | D2 | SSS101 | PT 6.2 Training 2 | 1.9 |
| 6 | E1 | MBBR3259 | Prep 5 Pumping + Cool Down | 148.4 |
| 10 | E2 | MBBL3237 | Finished Ready to go Final scan | 295.4 |
| 8 | F1 | MBBL3216 | Prep 5 Pumping + Cool Down | 294.2 |
| 3 | F2 | MBAL3225 | PT 6.6 Training 6 | 2.5 HV |

Temperature data are taken from TBSM18 site

Coordinator this week: Vittorio; MTM support on call :   16-3602 .

15 named  Magnets Tested or 16 Magnet  tests  cycles:

13 dipoles( 2 with MM)+ 2 SSS( 0 with MM ) +  0  SSSS     Disconnected after tests last week ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

AOB

## Tests

| Magnets under Test from 14-11-2004 to 20-11-2004 |
| --- |
| - | Bench | Magnet | Shafts | Start Date . | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total |  |  |
| 1 | TBA1 | MBAR1134 |  | 10-11-2004 | 23 h. | 30 h. | 25 h. | 14 h. | 8 h. | 14-11-2004 | 96 hours |  |  |
| 2 | TBA1 | MBBL3220 |  | 14-11-2004 | 28 h. | 43 h. | 31 h. | 15 h. | 13 h. | 20-11-2004 | 144 hours |  |  |
| 3 | TBA2 | MBBL2112 |  | 11-11-2004 | 30 h. | 55 h. | 27 h. | 15 h. | 6 h. | 17-11-2004 | 144 hours |  |  |
| 4 | TBB1 | SSS042 |  | 06-11-2004 | 38 h. | 62 h. | 111 h. | - | - | 15-11-2004 | 216 hours |  |  |
| 5 | TBB1 | SSS042 |  | 15-11-2004 | 0 h. | 15 h. | 17 h. | 10 h. | 9 h. | 18-11-2004 | 72 hours |  |  |
| 6 | TBB2 | MBBR3241 |  | 09-11-2004 | 44 h. | 60 h. | 20 h. | 22 h. | 7 h. | 16-11-2004 | 168 hours |  |  |
| 7 | TBC1 | MBAR1138 |  | 11-11-2004 | 38 h. | 53 h. | 55 h. | 22 h. | 7 h. | 18-11-2004 | 168 hours |  |  |
| 8 | TBC2 | MBAR3200 |  | 08-11-2004 | 21 h. | 46 h. | 46 h. | 14 h. | 4 h. | 14-11-2004 | 144 hours |  |  |
| 9 | TBC2 | MBBL2119 |  | 14-11-2004 | 24 h. | 51 h. | 19 h. | 25 h. | 10 h. | 19-11-2004 | 120 hours |  |  |
| 10 | TBD2 | SSS071 |  | 04-11-2004 | 149 h. | 35 h. | 83 h. | 8 h. | 10 h. | 17-11-2004 | 312 hours |  |  |
| 11 | TBE1 | MBAL2117 |  | 15-11-2004 | 25 h. | 44 h. | 21 h. | 15 h. | 12 h. | 20-11-2004 | 120 hours |  |  |
| 12 | TBE1 | MBBL1164 |  | 10-11-2004 | 28 h. | 65 h. | 15 h. | 18 h. | 5 h. | 15-11-2004 | 120 hours |  |  |
| 13 | TBE2 | MBAL2097 |  | 12-11-2004 | 0 h. | 37 h. | 28 h. | 23 h. | 4 h. | 16-11-2004 | 96 hours |  |  |
| 14 | TBF1 | MBBL1147 |  | 11-11-2004 | 53 h. | 43 h. | 22 h. | 31 h. | 13 h. | 18-11-2004 | 168 hours |  |  |
| 15 | TBF1 | MBBL1167 |  | 18-11-2004 | - | - | - | - | - | 20-11-2004 | 48 hours |  |  |
| 16 | TBF2 | MBAL1159 |  | 08-11-2004 | 29 h. | 48 h. | 47 h. | 15 h. | 7 h. | 14-11-2004 | 144 hours |  |  |
| 17 | TBF2 | MBBR3244 |  | 14-11-2004 | 25 h. | 32 h. | 21 h. | 13 h. | 14 h. | 19-11-2004 | 120 hours |  |  |

### Quench Information

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBAR1134 | 12046 A. (D2-L-CFB) | 12362 A. (D1-U-MRB) |  | - | - | - | - | - | - | - | - | - | - |
| 2 | MBBL3220 | 11474 A. (D2_U-MRB) | 12024 A. (D2_U_CFB) | 12284 A. (D2_U) | 12406 A. (D1-U-CF4) | 12576 A. (D2_L_CF_) |  | - | - | - | - | - | - | - |
| 3 | MBBL2112 | 10970 A. (D2-U) | 12033 A. (D2-L) |  | - | - | - | - | - | - | - | - | - | - |
| 4 | SSS042 | 10855 A. (QE-12) | 11105 A. (QI-34) | 11856 A. (QE-34) | 11998 A. (QE-12) | 11987 A. (QI_34) | 12291 A. (QI_34) | 12452 A. (QI-34) | 12674 A. (QI-34) | 12325 A. (QI_12) |  | - | - | - |
| 5 | SSS042 | 12199 A. (QE-12) | 12507 A. (QE-34) |  | - | - | - | - | - | - | - | - | - | - |
| 6 | MBBR3241 | 11859 A. (D2_U) | 11387 A. (D2-U) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 7 | MBAR1138 | 11500 A. (D1-L-S01) | 12025 A. (D2-L-S13) | 12172 A. (D1_U_S13) |  | - | - | - | - | - | - | - | - | - |
| 8 | MBAR3200 | 9429 A. (D2_L) | 10992 A. (D2_L) | 11368 A. (D2_L) | 11874 A. (D1-U) | 12246 A. (D1 L) | 12340 A. (D2-L) | 12630 A. (D1_L) | 12850 A. | - | - | - | - | - |
| 9 | MBBL2119 | 11429 A. (D1-U) | 12503 A. (D1-U) |  | - | - | - | - | - | - | - | - | - | - |
| 10 | SSS071 | 12480 A. (QE_12) | 12632 A. (QI_34) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 11 | MBAL2117 | 11851 A. (D2_U) | 12489 A. (D2-U) |  | - | - | - | - | - | - | - | - | - | - |
| 12 | MBBL1164 | 11885 A. (D1_L) | 12295 A. (D1-L) |  | - | - | - | - | - | - | - | - | - | - |
| 13 | MBAL2097 | 12700 A. (D2-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 14 | MBBL1147 | 12060 A. (D2_U) | 12284 A. (D2_U) |  | - | - | - | - | - | - | - | - | - | - |
| 15 | MBBL1167 |  | -REMOVED: CFB LEAK | - | - | - | - | - | - | - | - | - | - | - |
| 16 | MBAL1159 | 11103 A. (D2 L) | 11815 A. (D1-L) | 12017 A. (D1-L) | 12365 A. (D2-L) | 12425 A. (D1-L) | 12414 A. (D1_L) | 12567 A. (D1_U) | 12730 A. (D1-L) | 12846 A. (D2_U) |  | - | - | - |
| 17 | MBBR3244 | 12808 A. (D2-L) | 12648 A. (D2-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| From 14-11-2004 to 20-11-2004 |
| - | Bench | Magnet Name | shafts | Start Date . | Connect Time | Wait +Cooling | Cold Tests | Wait +Warming | Disconnect Time | End Date . | Total | Q |
| 1 | TBF2 | MBAL1159 | False | 08-11-2004 | 29 h. | 48 h. | 47 h. | 15 h. | 7 h. | 14-11-2004 | 6 days | 9 |
| 2 | TBF2 | MBBR3244 | False | 14-11-2004 | 25 h. | 32 h. | 21 h. | 13 h. | 14 h. | 19-11-2004 | 5 days | 2 |
| 3 | TBF1 | MBBL1147 | False | 11-11-2004 | 53 h. | 43 h. | 22 h. | 31 h. | 13 h. | 18-11-2004 | 7 days | 2 |
| 4 | TBF1 | MBBL1167 | False | 18-11-2004 | 98 h. | 0 h. | 0 h. | 0 h. | -57 h. | 20-11-2004 | 2 days | 0 |
| 5 | TBE2 | MBAL2097 | False | 12-11-2004 | 0 h. | 37 h. | 28 h. | 23 h. | 4 h. | 16-11-2004 | 4 days | 1 |
| 6 | TBE1 | MBAL2117 | False | 15-11-2004 | 25 h. | 44 h. | 21 h. | 15 h. | 12 h. | 20-11-2004 | 5 days | 2 |
| 7 | TBE1 | MBBL1164 | False | 10-11-2004 | 28 h. | 65 h. | 15 h. | 18 h. | 5 h. | 15-11-2004 | 5 days | 2 |
| 8 | TBD2 | SSS071 | False | 04-11-2004 | 149 h. | 35 h. | 83 h. | 8 h. | 10 h. | 17-11-2004 | 13 days | 2 |
| 9 | TBC2 | MBAR3200 | False | 08-11-2004 | 21 h. | 46 h. | 46 h. | 14 h. | 4 h. | 14-11-2004 | 6 days | 7 |
| 10 | TBC2 | MBBL2119 | False | 14-11-2004 | 24 h. | 51 h. | 19 h. | 25 h. | 10 h. | 19-11-2004 | 5 days | 2 |
| 11 | TBC1 | MBAR1138 | True | 11-11-2004 | 38 h. | 53 h. | 55 h. | 22 h. | 7 h. | 18-11-2004 | 7 days | 3 |
| 12 | TBB2 | MBBR3241 | False | 09-11-2004 | 44 h. | 60 h. | 20 h. | 22 h. | 7 h. | 16-11-2004 | 7 days | 2 |
| 13 | TBB1 | SSS042 | False | 06-11-2004 | 38 h. | 62 h. | 111 h. | 169 h. | -169 h. | 15-11-2004 | 9 days | 9 |
| 14 | TBB1 | SSS042 | False | 15-11-2004 | 0 h. | 15 h. | 17 h. | 10 h. | 9 h. | 18-11-2004 | 3 days | 2 |
| 15 | TBA2 | MBAR3204 | False | 17-11-2004 | 46 h. | 26 h. | 23 h. | 14 h. | 1 h. | 18-11-2004 | 1 days | 2 |
| 16 | TBA2 | MBBL2112 | False | 11-11-2004 | 30 h. | 55 h. | 27 h. | 15 h. | 6 h. | 17-11-2004 | 6 days | 2 |
| 17 | TBA1 | MBAR1134 | False | 10-11-2004 | 23 h. | 30 h. | 25 h. | 14 h. | 8 h. | 14-11-2004 | 4 days | 2 |
| 18 | TBA1 | MBBL3220 | True | 14-11-2004 | 28 h. | 43 h. | 31 h. | 15 h. | 13 h. | 20-11-2004 | 6 days | 5 |

from 13-11-2004 to 20-11-2004

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday _16_A | All benches | Temperature is increasing. | ACR |  | Interlock problem. Pumping stopped. |
| Tuesday _16_N | TBE2 | MTF not accessible with the mobic | TS | MTF | OK ½ hour after. |
| Tuesday _16_N | TBD1 | Qloc error during IAP | MTM | IAP |  |
| Tuesday _16_N | TBD1 | Provoked quench HF at 1,5 kA performed 2 times but no discharge of QH 3 and 4. | MTM |  | TC contacted. He decided to increase the quench current ( 2k A, 3 kA) |
| Wednesday _17_N | TBF2 | Detraining occurred in 3244 (12808 A then 12648) | MTM |  | TC decided to perform a third one. |
| Wednesday _17_N | TBD1 | MQ checks for MM with shafts. End field polarity errors | MTM | Display | Guy contacted. He advised to proceed. Color code adapted to the dipole. Changes will be done during the shut down. |
| Thursday _18_M | TBA2 | Quench localisation with LQA not coherent for the apertures with VTaps | MTM |  | Guy and Maryline checked the connection. Discussion with M.Calvi. A different logic in the connection was applied. So the connectors ap1-ap2 were inverted in the CFB side. Corrected. Now cables are labelled. |
| Thursday _18_N | TBF1 | HV test could not be performed: “megger could not be put in remote mode”. | MTM |  | Repeated 3 times then rack changed. |
| Friday_19_A | TBF2 | Cryo leak detected in the 3225. (leak in one foot of the magnet, joint not good.) | ICS? |  | NC opened by L.Herblin. ACR decided to still go on with the tests. |
| Friday_19_N | TBE2 | C11 connector damaged |  |  | Proceed with the tests but with special care in the plug in and plug out. |
| Saturday_20_M | TBE2 | SPA occurred during the ramp to 12000 A for fast de-excitation test. | ? |  | Origin not clear? |
| Saturday_20_M | TBD1 | Wire broken during roll angle measurements | MTM |  |  |
| Saturday_20_A | TBA2 | Water leak in the power cable. | MTM |  | Guy came: he checked and advised to proceed because it was not critical but asked to stop the water flow after the power test. Repaired by Giorgio Monday. |
| Saturday_20_A | TBD1 | HV test after power test. Orbit dipole vs ground failed. | MTM | HV | OK when the step was repeated but failed in the third attempt. Repeated a fourth time then OK. |
| Saturday_20_N | TBB2 | When the shaft 22 was removed, one sector joint was found to be unstuck. | MTM |  | Default not detected during measurements, connector and cables not damaged. Shaft shocked during removal? Stephane ask to put the shaft out of the circuit. The sector will be electrically checked and the sector repaired (Action Olaf and his team). |
| Sunday_21_A | TBC1 | Incorrect display of the T821 value : 80 K and the magnet is at 1.9 K | MTM |  |  |
| Sunday_21_N | TBB1 | Leak found on the SSS 614 (localised in a tube inside the magnet on MRB side) |  |  | NC will be opened. SSSS sent back? |
| Sunday_21_N | TBF1 | Leak found on the TBF1 test bench (3216 MB) coming from one “flexible” inside the CFB. | ACR |  | L.Herblin aware. ACR team changed the flexible Monday. |
| Sunday_21_N | TBA2 | Current lead B overheated. Banana plug damaged. |  |  | Stéphane informed Guy Monday morning. |
| Monday_22_M | TBB1 | Connector of the cable 16 in the XMT.95 HV rack (N 4) is broken. | MTM |  | Guy informed. This rack is out of use for the moment. He will inform Richard for the repair Wednesday. |