vc/4-Jul-05

### Week 27  starting 4 July 05

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday  04 July 05 @: 7/4/2005 12:45:00 PM

|  | A1 | MBBL3095 | CR 1 Leak Test |  |
| --- | --- | --- | --- | --- |
|  | A2 | MBAR3372 | Prep 2.2 IAP @ warm HF |  |
|  | B1 | SSS148 | ICS 6 Disconnect Magnet WP07 |  |
|  | B2 | SSS205 | Prep 5 Cool Down |  |
|  | C1 | MBBR3314 | Prep 5 Cool Down |  |
|  | C2 | MBAR3302 | PT 13.2 Resist. Meas. |  |
|  | D1 | SSS203 | MM - correctors |  |
|  | D2 | SSS640 | PT 12 Warm Up |  |
|  | E1 | MBBR3273 | PT 12 Warm Up |  |
|  | E2 | MBBL2161 | Finished Ready to go Final scan |  |
|  | F1 | MBAL2051 | ICS 3 Traveller after warm test |  |
|  | F2 | MBAR3321 | PT 12 Warm Up |  |

Temperature data are taken from TBSM18 site

Coordinator this week: Marta;MTM support on call :  16-3602

19 complete Magnet Tests cycles   ( SSS280  ROBTC, 2193 ? )

13  dipoles( 1 with MM )+ 5  SSS( 0  with MM) +  1 SSSS (with MM)

[2513   ok on 2nd quench but put on standby to avoid MAS Group controversies]

Disconnected or ROBTC after tests last week ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- General Points  : MTF & Database Problems on Monday (yesterday)

- AOB

| Magnets under Test from 26-06-2005 to 02-07-2005 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |  |  |
| 1 | TBA1 | MBBL1232 |  |  | 20-06-2005 | 23 h. | 90 h. | 18 h. | 15 h. | 19 h. | 27-06-2005 | 165 h. | Stripping |  |  |
| 2 | TBA1 | MBBL3098 |  |  | 27-06-2005 | 48 h. | 25 h. | 21 h. | 15 h. | 9 h. | 02-07-2005 | 118 h. | Stripping |  |  |
| 3 | TBA2 | MBAL2193 |  |  | 26-06-2005 | 28 h. | 20 h. | 44 h. | 11 h. | 0 h. | 30-06-2005 | 103 h. | Not Found or Thermal cycle |  |  |
| 4 | TBA2 | MBBL1235 |  |  | 19-06-2005 | 34 h. | 34 h. | 69 h. | 16 h. | 14 h. | 26-06-2005 | 167 h. | Stripping |  |  |
| 5 | TBB1 | SSS121 |  |  | 26-06-2005 | 38 h. | 15 h. | 15 h. | 10 h. | 9 h. | 30-06-2005 | 87 h. | Stripping |  |  |
| 6 | TBB1 | SSS221 |  |  | 22-06-2005 | 32 h. | 21 h. | 15 h. | 7 h. | 23 h. | 26-06-2005 | 98 h. | Stripping |  |  |
| 7 | TBB2 | SSS287 |  |  | 28-06-2005 | 44 h. | 13 h. | 17 h. | 8 h. | 12 h. | 02-07-2005 | 94 h. | Stripping |  |  |
| 8 | TBB2 | SSS290 |  |  | 23-06-2005 | 28 h. | 26 h. | 36 h. | 15 h. | 11 h. | 27-06-2005 | 116 h. | Stripping |  |  |
| 9 | TBC1 | MBAR2513 |  |  | 27-06-2005 | 41 h. | 28 h. | 16 h. | 16 h. | 14 h. | 02-07-2005 | 115 h. | Stand By |  |  |
| 10 | TBC1 | MBBL1234 |  |  | 24-06-2005 | 20 h. | 22 h. | 19 h. | 13 h. | 9 h. | 27-06-2005 | 83 h. | Stripping |  |  |
| 11 | TBC2 | MBBR3357 |  |  | 25-06-2005 | 36 h. | 26 h. | 12 h. | 13 h. | 26 h. | 29-06-2005 | 113 h. | Stripping |  |  |
| 12 | TBD1 | SSS280 |  |  | 20-06-2005 | 36 h. | 42 h. | 62 h. | 16 h. | 0 h. | 26-06-2005 | 156 h. | Not Found or Thermal cycle |  |  |
| 13 | TBD1 | SSS280 |  |  | 27-06-2005 | 0 h. | 11 h. | 10 h. | 9 h. | 23 h. | 29-06-2005 | 53 h. | Stripping |  |  |
| 14 | TBD2 | SSS616 |  |  | 18-06-2005 | 51 h. | 27 h. | 84 h. | 62 h. | 31 h. | 28-06-2005 | 255 h. | Stand By |  |  |
| 15 | TBE1 | MBBL2165 |  |  | 22-06-2005 | 33 h. | 21 h. | 41 h. | 17 h. | 16 h. | 27-06-2005 | 128 h. | Stripping |  |  |
| 16 | TBE1 | MBBR3358 |  |  | 27-06-2005 | 29 h. | 22 h. | 15 h. | 13 h. | 11 h. | 01-07-2005 | 90 h. | Stripping |  |  |
| 17 | TBE2 | MBBR3355 |  |  | 23-06-2005 | 29 h. | 40 h. | 19 h. | 14 h. | 34 h. | 28-06-2005 | 136 h. | Stripping |  |  |
| 18 | TBF1 | MBAL1228 |  |  | 21-06-2005 | 60 h. | 28 h. | 38 h. | 18 h. | 35 h. | 29-06-2005 | 179 h. | Stripping |  |  |
| 19 | TBF2 | MBAR3330 |  |  | 25-06-2005 | 29 h. | 29 h. | 37 h. | 13 h. | 11 h. | 30-06-2005 | 119 h. | Stripping |  |  |

### Quench Information

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBBL1232 | 11284 A. (D2-L) | 12174 A. (D1-U) | 12354 A. (D2-U) |  | - | - | - | - | - | - | - | - | - |
| 2 | MBBL3098 | 9941 A. (D2-U) | 12215 A. (D2-L) | 12347 A. (D2_U) |  | - | - | - | - | - | - | - | - | - |
| 3 | MBAL2193 | 10809 A. (D1-L) | 11768 A. (D2-U) | 12198 A. (D1-L) | 12409 A. (D2_U) | 12608 A. (D2_U) | 12669 A. (D2_U) | 12727 A. (D1_U) | 12544 A. (D!_U) | 12711.9 A. (D1-U) |  | - | - | - |
| 4 | MBBL1235 | 11606.6 A. (D1-L-S01) | 11972.4 A. (D1-L-S01) | 12206.3 A. (D1_U-S01) | 12393 A. (D1-U-S13) | 0 A. (No Data) | 12500 A. (No Data) | 12708 A. (D1-L-S12) | 12848.1 A. (D1-U-S01) | 12850 A. | - | - | - | - |
| 5 | SSS121 | 12325 A. (QE-12) | 12783 A. (QE-12) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 6 | SSS221 | 11945 A. (QE_34) | 12634 A. (QE_12) | 12845.3 A. (QE-34) |  | - | - | - | - | - | - | - | - | - |
| 7 | SSS287 | 11792 A. (QI-12) | 12055 A. (QI_12) | 12767 A. (QE_34) |  | - | - | - | - | - | - | - | - | - |
| 8 | SSS290 | 11381.5 A. (QE_12) | 11887.7 A. (QE-12) | 12107 A. (QE_12) | 12326.2 A. (QE_12) | 12494 A. (QE-12) | 12689.9 A. (QE-12) | 12710 A. (QI-12) | 12791 A. (QE-34) | 12850 A. | - | - | - | - |
| 9 | MBAR2513 | 10817 A. (D2 - U) | 12496 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 10 | MBBL1234 | 11416 A. (D2-U) | 12224.8 A. (D1-L) | 12581 A. (D1 - U) |  | - | - | - | - | - | - | - | - | - |
| 11 | MBBR3357 | 12491.3 A. (D2_U) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 12 | SSS280 | 11563 A. (QI-12) | 11649.6 A. (QE-12) | 12082.2 A. (QE-12) | 12331 A. (QI-12) | 12464 A. (QI-12) | 12520 A. (QE_34) | 12547 A. (QE-34) | 12631 A. (QE-12) | 12692.4 A. (QI-12) |  | - | - | - |
| 13 | SSS280 | 11695.2 A. (QE-34) | 12260 A. (QE-12) |  | - | - | - | - | - | - | - | - | - | - |
| 14 | SSS616 | 5712.4 A. (MQM_Int.) | 5850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 15 | MBBL2165 | 10250 A. (D2-L) | 11475.7 A. (D2-U) | 12238 A. (D1-L) | 12021.2 A. (D1_L) | 12260.8 A. (D1-L) | 11991.6 A. (D1-L) | 12337.7 A. (D1-U) | 12550 A. (D1 - U) | 12850 A. | - | - | - | - |
| 16 | MBBR3358 | 12483.7 A. (D1_L) | 12513.9 A. (D1-U) | 12759 A. (D2-L) |  | - | - | - | - | - | - | - | - | - |
| 17 | MBBR3355 | 12165 A. (D2-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 18 | MBAL1228 | 10705 A. (D1_U) | 11759 A. (D2_U) | 12121 A. (D1-L) | 12575 A. (No Data) | 12798 A. (D2 - L) | 12850 A. | - | - | - | - | - | - | - |
| 19 | MBAR3330 | 12686 A. (D2-L-S01) | 12758.1 A. (D2-L-S05) | 12850 A. | - | - | - | - | - | - | - | - | - | - |

PROJECTION TO COMPLETION 4 July 05

| Assumption : Testing Time (Upto may 05) : Dipole -131 hrs;SSS- 143 hrs, After May-05, Dipole - 120 Hrs, ARCSSS - 125 Hrs, IR SSS - 10 days |
| --- |
| Date | Magnets per Month Dipoles | Magnets per Month ARC SSS | Magnets per Month IR SSS | Cumulative Dipoles | Cumulative ARC SSS | Cumulative IR SSS | Cumulative Total | Magnets per Month | Configuration |
| Dec-03 | 95 | 2 |  | 95 | 2 | 0 | 97 |  | D-6/AS-1 |
| Jan-04 | 1 |  |  | 96 | 2 | 0 | 98 | 1 | D-8 |
| Feb-04 | 28 | 2 |  | 124 | 4 | 0 | 128 | 30 |  |
| Mar-04 | 37 | 1 |  | 161 | 5 | 0 | 166 | 38 |  |
| Apr-04 | 36 | 2 |  | 197 | 7 | 0 | 204 | 38 |  |
| May-04 | 30 | 1 |  | 227 | 8 | 0 | 235 | 31 | D-9/AS-1 |
| Jun-04 | 37 | 3 |  | 264 | 11 | 0 | 275 | 40 | D-10/AS-2 |
| Jul-04 | 38 | 6 |  | 302 | 17 | 0 | 319 | 44 | D-9/AS-3 |
| Aug-04 | 43 | 7 |  | 345 | 24 | 0 | 369 | 50 |  |
| Sep-04 | 41 | 6 | 1 | 386 | 30 | 1 | 417 | 48 | D-8/AS-3/IS-1 |
| Oct-04 | 47 | 10 | 1 | 433 | 40 | 2 | 475 | 58 |  |
| Nov-04 | 48 | 11 |  | 481 | 51 | 2 | 534 | 59 | D-9/AS-2/IS-1 |
| Dec-04 | 15 | 3 | 1 | 496 | 54 | 3 | 553 | 19 |  |
| Jan-05 | 6 | 1 | 0 | 502 | 55 | 3 | 560 | 7 | D-9/AS-2/IS-1 |
| Feb-05 | 43 | 13 | 2 | 545 | 68 | 5 | 618 | 58 |  |
| Mar-05 | 51 | 13 | 2 | 596 | 81 | 7 | 684 | 66 |  |
| Apr-05 | 51 | 21 | 0 | 647 | 102 | 7 | 756 | 72 | D-8/AS-4 |
| May-05 | 48 | 27 | 1 | 695 | 129 | 8 | 832 | 76 | D-8/AS-3/IS-1 |
| Jun-05 | 46 | 21 | 3 | 741 | 150 | 11 | 902 | 70 |  |
| Jul-05 | 46 | 12 | 4 | 787 | 162 | 15 | 964 | 62 | D-8/AS-2/IS-1 |
| Aug-05 | 48 | 12 | 4 | 835 | 174 | 19 | 1028 | 64 | 1 bench special tests 8 weeks |
| Sep-05 | 46 | 18 | 4 | 881 | 192 | 23 | 1096 | 68 | D-8/AS-3/IS-1 |
| Oct-05 | 46 | 18 | 4 | 927 | 210 | 27 | 1164 | 68 |  |
| Nov-05 | 46 | 18 | 4 | 973 | 228 | 31 | 1232 | 68 |  |
| Dec-05 | 23 | 9 | 4 | 996 | 237 | 35 | 1268 | 36 |  |
| Jan-06 | 0 | 0 | 0 | 996 | 237 | 35 | 1268 | 0 | SHUTDOWN |
| Feb-06 | 36 | 18 | 4 | 1032 | 255 | 39 | 1326 | 58 |  |
| Mar-06 | 48 | 18 | 4 | 1080 | 273 | 43 | 1396 | 70 |  |
| Apr-06 | 48 | 18 | 4 | 1128 | 291 | 47 | 1466 | 70 |  |
| May-06 | 36 | 25 | 8 | 1164 | 316 | 55 | 1535 | 69 | D-6/AS-4/IS-2 |
| Jun-06 | 36 | 25 | 8 | 1200 | 341 | 63 | 1604 | 69 |  |
| Jul-06 | 36 | 25 | 8 | 1236 | 366 | 71 | 1673 | 69 |  |
| Aug-06 | 36 | 25 | 8 | 1272 | 391 | 79 | 1742 | 69 |  |
| Sep-06 | 36 | 25 | 8 | 1308 | 416 | 87 | 1811 | 69 |  |
| Oct-06 | 36 | 19 | 4 | 1344 | 435 | 91 | 1870 | 59 |  |
| Nov-06 | 24 |  |  | 1368 | 435 | 91 | 1894 | 24 |  |
| Dec-06 |  |  |  | 1368 | 435 | 91 | 1894 | 0 |  |
| Jan-07 |  |  |  | 1368 | 435 | 91 | 1894 | 0 |  |
| Feb-07 |  |  |  | 1368 | 435 | 91 | 1894 | 0 |  |
| Mar-07 |  |  |  | 1368 | 435 | 91 | 1894 | 0 |  |
| Apr-07 |  |  |  | 1368 | 435 | 91 | 1894 | 0 |  |
| May-07 |  |  |  | 1368 | 435 | 91 | 1894 | 0 |  |
| Jan 2005 |  |  |  |  |  |  |  |  |  |
| Basic Targets | 1232 | 360 | 114 | 114 (IR SSS)=50 (MS) + 32 (DS) + 32 (DS-MQ Type) |
| Re-Tested | 135.52 | 39.6 | 12.54 |  |  |  |  |  |  |
| Probable Target | 1367.52 | 399.6 | 126.54 |  |  |  |  |  |  |
| Total Magnets | 1893.66 |  |  |  | 04-Jul-05 |  |  |  |  |
|  |  |  |  |  | Basic Targets | 1232 | 392 | 82 |  |
| Estimates with Cryo Enchancement |  |  |  |  | Re-Tested | 135.52 | 43.12 | 9.02 |  |
| Dipoles |  | ARC-SSS |  |  | Probable Target | 1367.52 | 435.12 | 91.02 |  |
| 8-Benches | 48 | 3- Benches | 18.78261 |  | Total Magnets | 1893.66 |  |  |  |
| 7-Benches | 42 | 4-Benches | 25.04348 |  |  |  |  |  |  |
| 6-Benches | 36 | 6-Benches | 37.56522 |  | Average Time 2005 |  |  | 04-Jul-05 |  |
| 9-Benches | 54 | 2- Benches | 12.52174 |  | Item | Dipoles | SSS |  |  |
| NOTE |  |  |  |  | Connect Time | 30 | 30 |  |  |
|  |  |  |  |  | Cooling Time | 30 | 20 |  |  |
| Average Time 2004 |  |  |  |  | Cold Test Time | 30 | 35 |  |  |
| Item | Dipoles | SSS |  |  | Warming Time | 15 | 10 |  |  |
| Connect Time | 30 | 82 |  |  | Disconnect Time | 15 | 20 |  |  |
| Cooling Time | 45 | 32 |  |  | Total Time | 120 | 115 |  |  |
| Cold Test Time | 34 | 75 |  |  |  |  |  |  |  |
| Warming Time | 20 | 12 |  |  |  |  |  |  |  |
| Disconnect Time | 8 | 8 |  |  |  |  |  |  |  |
| Total Time | 137 | 209 |  |  |  |  |  |  |  |

FAULTS from LAST WEEK

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday _28_M | TBF2 | Verrin damaged impeding to align the TRU. | MTM |  | MTM-MECA team informed. They solved the problem. |
| Tuesday _28_A | TBC1 | MB2513: he temperature sensor is reading 241K and not 291 K. | MTM |  | Giorgio updated the coefficients coming from MTF. |
| Tuesday _28_A | ALL | Stop of pumping because of an intervention (instrumentation to be repaired). | ACR |  | 2hours of stop |
| Tuesday _28_A | ALL | IAP error H2-TminV=1659ms. | MTM |  | Maryline consulted. She gave the OK. |
| Tuesday _28_N | TBF2 | MM2 on MB3330: No current acquisition in aperture A1 during cleansing cycle. | MTM | MMP | Giorgio advised to continue. |
| Tuesday _28_N | TBF2 | MM2 on MB3330. Some data not exported. Invalid format error. | MTM | MMP |  |
| Tuesday _28_N | TBF2 | Pumping problems: long delays to get SSS121 below 4.4K to proceed with test sequence | ACR? MTM? |  | Capacity of pumping at 20g/s not 26g/s but this cannot explain the slow down. SSS121 in priority 3. Did the magnets with priority 1 and 2 quench before? |
| Tuesday _28_N | TBA2 | MM3 on MB3330: current reading problem at 550 A during the ramp up of the current (full load line) | AB/CO? |  | Maryline will investigate the problem with Hubert. |
| Wednesday _29_A | TBA2 | Training 6 on MB2193: Vjump >10 V~ 11V for D1-D2 | MTM |  | Giorgio called. |
| Wednesday _29_A Wednesday_29_N Thursday_30_M Thursday_30_A | TBA2 | SMTMS not working. WEB server not accessible. | MTM |  | OP team contacted A.Wagner in the after noon and during the night. |
| Wednesday _29_N | TBD2 | Leak in the manchette (SSS640) | AB/CO |  | ICS has been informed to replace the joint of manchette |
| Thursday _30_N | TBC1 | Hf DAQ not working properly. Error 2 in arming. | AB/CO |  | PT8 postponed after HV test final. |
| Thursday _30_N | TBC1 | Hf DAQ not working properly. Error 2 in arming. | AB/CO |  | PT8 postponed after HV test final. |
| Thursday _30_N | TBD2 | Survey to be done after warm X-Y measurements in SSS203. SIMCO called but the team was not booked. | MTM |  | Giorgio did the survey early in the morning. |
| Friday _01_M | TBA2 | Potaim triggers on Vclamp D before IAP@warm on SSS148. | ICS |  | ICS called to check the connection. |
| Friday _01_A | TBD2 | SPA occurred due to cryo-loss (lead temp high) while Roll angle measurement was running. Idem during filed strength measurements (2 times) | ACR |  |  |
| Friday _01_A | TBA1 | Communication error between PLCSE and server. TEMA not running. | AB/CO |  | Giorgio reseted PLCSE and the problem was solved |
| Saturday _02_A | TBD2 | Wrong results for field strength measurements at 2500 A. | MTM |  | Wire re-centred correctly and measurements repeated. |
| Saturday _02_A | TBD2 | SPA occurred during field strength measurements at 2500 A. | ? |  |  |
| Sunday _03_M | TBF | TRU 4 could not be used because hand wheel gear broken |  |  | ICS changed with TRU 1. |
| Sunday _03_M | TBD1 | IAP @cold: not correct values. |  |  | Giorgio called. |
| Sunday _03_M | TBD1 | Connector on TBD1 of shaft 36 (aperture 1) does not fully connect, | MTM |  | Giorgio called. |
| Sunday _03_M | TBD1 | Q-loc on TBD1: because the cabling is tuned towards MB's, some channels can not be compensated enough to full fill IAP criteria. |  |  |  |