### EV/18-July-05

### Week 30  starting 27 June 05

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday  25 July 05 @: 7/25/2005 3:08:55 PM

11 A1 MBAR3371 Prep 0 Scan Bench 299.2 8 A2 MBAL2170 ICS 4 Final connection 298.49 1 B1 SSS173 PT 6.2 Training 2 1.90 7 B2 SSS195 Prep 0 Scan Bench 299.11 4 C1 MBBR3360 PT 12 Warm Up 278.49 5 C2 MBBL3121 Prep 5 Cool Down 298.31 9 D1 SSS152 PT 13.2 Resist. Meas. 299.02 12 D2 FREE Bench MAINTENANCE 298.76 2 E1 MBBL3115 PT 6.1 Training 1 5.37 6 E2 MBAL1207 Prep 1 Lyre Test 298.49 10 F1 MBBR3336 PT 13.2 Resist. Meas. 298.58 3 F2 MBAR3367 Prep 5 Cool Down 88.98

Temperature data are taken from TBSM18 site

Coordinator this week: Marco;MTM support 16-3602

13 complete Magnet Tests cycles

9 dipoles( MM )+ 4 SSS( 1 with special Thermal cycle without MM & SSW )

Disconnected or ROBTC after tests last week ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- General Points :

- Special S4 (Florence)

- Special Tests D2 : Silver shoes repaired, Q4 S4.

- Rotary Switch cluster B difficult to used.

- Rotary Switch for Corrector powering.

- AOB

# From 7/17/2005 to 7/23/2005

| - | Bench | Magnet | Shafts | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | TBA1 | MBBL2189(2) |  | 12-07-2005 | 30 h. | 25 h. | 50 h. | 17 h. | 0 h. | 17-07-2005 | 122 h. | Thermal cycle |
| 2 | TBA1 | MBBL2189(2) |  | 17-07-2005 | 3 h. | 27 h. | 22 h. | 13 h. | 8 h. | 20-07-2005 | 73 h. | Stripping |
| 3 | TBB1 | SSS199 |  | 13-07-2005 | 29 h. | 133 h. | 29 h. | 10 h. | 16 h. | 22-07-2005 | 217 h. | Stripping |
| 4 | TBB2 | SSS204 |  | 08-07-2005 | 172 h. | 13 h. | 34 h. | 12 h. | 11 h. | 17-07-2005 | 242 h. | Stand By |
| 5 | TBC1 | MBAR3369 |  | 16-07-2005 | 34 h. | 50 h. | 39 h. | 6 h. | 13 h. | 22-07-2005 | 142 h. | Stripping |
| 6 | TBC2 | MBAL1246 |  | 19-07-2005 | 14 h. | 48 h. | 17 h. | 15 h. | 20 h. | 23-07-2005 | 114 h. | Stripping |
| 7 | TBC2 | MBBL3085 |  | 15-07-2005 | 26 h. | 24 h. | 14 h. | 13 h. | 8 h. | 18-07-2005 | 85 h. | Stripping |
| 8 | TBD1 | SSS217 |  | 12-07-2005 | 33 h. | 25 h. | 135 h. | 3 h. | 16 h. | 21-07-2005 | 212 h. | Stand By |
| 9 | TBD2 | SSS617 |  | 15-07-2005 | 52 h. | 16 h. | 4 h. | 15 h. | 9 h. | 19-07-2005 | 96 h. | Thermal cycle |
| 10 | TBE1 | MBAL3109 |  | 16-07-2005 | 45 h. | 54 h. | 17 h. | 15 h. | 9 h. | 22-07-2005 | 140 h. | Stripping |
| 11 | TBE2 | MBAR3373 |  | 13-07-2005 | 34 h. | 25 h. | 27 h. | 21 h. | 9 h. | 18-07-2005 | 116 h. | Stripping |
| 12 | TBF1 | MBBL2206 |  | 13-07-2005 | 35 h. | 30 h. | 15 h. | 26 h. | 8 h. | 18-07-2005 | 114 h. | Stripping |
| 13 | TBF2 | MBBL3126 |  | 16-07-2005 | 44 h. | 46 h. | 15 h. | 15 h. | 10 h. | 22-07-2005 | 130 h. | Stripping |

Quench Information

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | TC Q1 | TC Q2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBBL2189 | 9160.2 A. (D1-L) | 11076 A. (D2-L) | 11904 A. (D2-L) | 12024.1 A. (D2_U) | 11098.9 A. (No Data) | 12426 A. (D1 - U) | 12655 A. (D2 - U) | 12307 A. (D2 - U) | 12667 A. (D2_U) | 12820 A. (D2-U) | 12700 A. (D2-U) |  |
| 2 | MBBL2189 | 12016.8 A. (D1-U) | 12828 A. (D2-U) |  | - | - | - | - | - | - | - |  |  |
| 3 | SSS199 | 11733 A. (QI-34) | 12401 A. (QE-12) | 12756 A. (QE_12) |  | - | - | - | - | - | - |  |  |
| 4 | SSS204 | 11450 A. (QI-34) | 11607 A. (QE_34) | 12337 A. (QE-34) | 12850 A. | - | - | - | - | - | - |  |  |
| 5 | MBAR3369 | 10255 A. (D1-U) | 12393.5 A. (D1_U) | 12648 A. (D2-U) |  | - | - | - | - | - | - |  |  |
| 6 | MBAL1246 | 11810 A. (D1-L) | 12019 A. (D2-L) | 12230 A. (D1-L) |  | - | - | - | - | - | - |  |  |
| 7 | MBBL3085 | 12600.9 A. (D1-U) | 12850 A. | - | - | - | - | - | - | - | - |  |  |
| 8 | SSS217 | 11813.1 A. (QE-34) | 12615.5 A. (QI_12) | 12836 A. (QI-12) | 12850 A. | 12850 A. | - | - | - | - | - | - |  |
| 9 | SSS617 | 5890 A. | - | - | - | - | - | - | - | - | - |  |  |
| 10 | MBAL3109 | 11687.1 A. (D2_L) | 12850 A. | - | - | - | - | - | - | - | - |  |  |
| 11 | MBAR3373 | 10700 A. (D1-U) | 11531 A. (D2-U) | 12852.2 A. (D1-U) | 12850 A. | - | - | - | - | - | - |  |  |
| 12 | MBBL2206 | 11926 A. (D2-L) | 12773 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - |  |  |
| 13 | MBBL3126 | 11843 A. (D1-U) | 12246 A. (D2-U) | 12594.2 A. (D2-L) |  | - | - | - | - | - | - |  |  |

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday _19_M Tuesday _19_N Tuesday _19_N | ALL Bench TBE1 TBC1 | Cryogenic Supervision lost. PLCSE communication error. Intercon lights do not flicker when we switch over to X2. Unable to run test PT4 due to interlocks, QheaterC_x1, PowerQH_OK. Potaim card red light on V_supra_D and Vsum_Ext_s. | ACR AB/CO |  | ACR piquet has been called by cryo team, and asked to wait 8:00. Antonio Tovar is not in call. Close Tema, reset server crate, ok after Call Equip Support for Intercon box problem |
| Wednesday _20_M Wednesday _20_M Wednesday _20_N | TBB1 TBD1 TBA2 TBB1 | HV could not be launched because of wrong cryo phase interlock, further power tests has been stopped because of no signal from LQA. Powering corrector GH-IJ are not possible to perform, because of a different cabling. | MTM MTM |  | Reinstallation of the programs was not done properly on this cluster, now it is solved. Richard Equipment Support has been informed. Richard has been informed during morning, and till the new rotary switch is not install, equipment support will switch between B1 to B2. |
| Thusday _21_N | TBF1 | Trigger on Potaim card Vbus_Ext & Vbus_Int. Unable to launch PT1 (partIII) AC compensation test on TBF1. Richard informed | MTM |  | Problem is caused by the INTERCON box not switching some of the main voltage taps of the dipole. I have shorted one cable on INTERCON so that we can go on with the tests on TBF1. But we can not switch it to X2, it needs an intervention to put INTERCON in normal configuration. Richard. |
| Friday_22_M Friday_22_M | TBC2 TBF | PT4, quench during SPA, below 70 amperes. Problem identified, it's due to 2 random different reason: 1st, the potaim card Number 2 was not working properly (it has benn changed). 2nd, It seems that we have a problem with the Power converter behaviour (AP/PO informed, they should perform some test on monday). SPA during ramping for first training Richard has interchanged the chassis for minimum energy with the one of cluster D which is not used on this cluster. | MTM MTM |  | The "variac" is destroyed and needs to be replaced. Richard. For the moment operators must perform an dico reset before each power test.Test aborted. |
| Friday _22_A | TBF | Switch between F1 to F2 or reverse way | MTM |  | Richard has put some sticker to help operation team to change this cabling during week end. |
| Friday _22_N | TBB2 | Files not transferred to the 'Storage/vol12' folder for SSS036_5. Data could not be validated for PT5.1 & PT6.1 | AB/CO |  | ? |
| Saturday_23_M | TBA1 | AC Signal wire above CFB partly broken. Needs to be soldered. | MTM |  | ? |
| Saturday_23_M | TBE1 | ICS informed and show that the wire for the V clamp connection is broken, not possible to connect it | MTM |  | ? |
| Saturday_23_A | TBB1 | IAP clamp connection of correctors could not be launched because of self generated trigger. ICS open sleeve to check the connection. | ICS |  | ICS found wrong connection and done the right connection. IAP clamp connection of correctors has been done successfully. |
| Saturday_23_A | TBF1 | MM mobile rack XMT.MY71 was not working. Amplifier error got during AutoTest. The Rack has been changed but there was problem with Scanning. Both the MOBIC are not working properly. Equipment support has been informed. | MTM |  | ? |
| Saturday_23_N | TBD1 | SSS152 HV at cold failed on (M(X)-D M(X)-F correctors and Sextupoles) | ? |  | Magnet will be signed stand by. |
| Sunday_24_M | TBF1 | during MM3 (Full loadline) ramping : SPA. |  |  | Test was relaunched. |
| Sunday _24_N | TBD1 | Communication failure between sunmta35 and PLCSE. The popup "Contacting PLCSE " comes up every 1-2 min. The same problem occured on 23/07/2005 also on TBD1. Then HV could not be started because of "wrong Cryo phase" | AB/CO |  | It was solved by switching OFF the PLCSE and then restarting. |
| Monday _25_N | TBF2 | Problem with HV test on bench F2 magnet 3367. at 3050v step of "cold initial before test connected to CFB" Dipole quench heaters versus ground current reading was about 10mA and error was generated. connections checked and everything seemed OK. | MTM |  | so rack changed from MY95 to MY93 and test relaunched. No errors appeared. Rack MY95 marked with sign signalling fault and that it should not be used until checked by eq supp. |