### CHOHAN /17--Oct- 05

### Week 42 starting 17 oct 05

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday  17 Oct 05 :  10/17/2005 11:59:26 AM

| 7 | A1 | MBBR1259 | Prep 2.2 IAP @ warm HF | 295.18 |
| --- | --- | --- | --- | --- |
| 2 | A2 | MBAR1265 | PT 10 Min. NRJ 11850 A | 4.81 |
| 8 | B1 | SSS654 | Prep 2.2 IAP @ warm HF | 294.73 |
| 11 | B2 | SSS049 | ICS 4 Final connection | 295.36 |
| 9 | C1 | MBAL2192 | ICS 4 Final connection | 293.57 |
| 1 | C2 | MBAR2222 | PT 9 CDAP HV | 1.91 |
| 10 | D1 | SSS292 | ICS 2 Connect Magnet (ICS) | 295.18 |
| 4 | D2 | SSS604 | FS23 MQ Strength @11850 | 1.90 |
| 5 | E1 | MBBL3411 | Prep 5 Cool Down | 96.67 |
| 12 | E2 | CRYO | Cryo leak repair | 295.44 |
| 6 | F1 | MBAR1268 | PT 3 QH Measure | 2.35 |
| 3 | F2 | MBBL2055 | PT 6.3 Training 3 | 49.28 |

Tempr. from TBSM18 site

Coordinator this week: Pierre; MTM support: 16-3602

14 complete Magnet Tests cycles  from 11 benches ( E2 still

under CFB repair)

9 dipoles + 3  SSS  + 2  SSSS

Disconnected or ROBTC after tests last week ( Sat Midnight to Sat midnight)

Situation From Cryogenics:  J-P Lamboy or ACR Rep.

No new magnet tested on E2 since 29 Sept (already 3 weeks !)

E2 CFB (leak) Repair whole Week this week again?  ( 11 benches usage only)

Special  Points :

- Special SSS on B1 : connection problems ?

- Special SSS604  on D2 :Great progress thanks to Jackie/Eric/Kevin/Roy shifts

During weekend; SSW was finished Sat . morning. Nothing done since; So how long now for Chaconsa?

- AOB :  Connector for Dipoles when they arrive (Eric/Giorgio)

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBBL2216 | 12049.7 A. (D1-U) | 12794 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 2 | MBAL1249 | 11527.3 A. (D1-U) | 12625.6 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 3 | MBBR1261 | 10919.9 A. (D1-L) | 12070 A. (D2-L) | 12265.8 A. (D2-L) |  | - | - | - | - | - | - | - | - | - |
| 4 | SSS629 | 5695 A. (MQM-I-34) | 5822 A. | - | - | - | - | - | - | - | - | - | - | - |
| 5 | SSS160 | 11838.1 A. (QE_34) | 12373 A. (QE_34) | 12500 A. (QE_12) |  | - | - | - | - | - | - | - | - | - |
| 6 | SSS349 | 11944.9 A. (QE-12) | 12184.7 A. (QI_34) | 12834.4 A. (QI-12) |  | - | - | - | - | - | - | - | - | - |
| 7 | MBBR1263 | 11398 A. (D1-L) | 11998.9 A. (D1-L) | 12184.3 A. (D1-L) | 12458 A. (D2-U) | 12613.1 A. (D1-U) | 12737.3 A. (D1-L) | 12844 A. (D2_U) | 12850 A. | - | - | - | - | - |
| 8 | MBBL2071 | 11888.1 A. (D2-L) | 12347.5 A. (D1-U) | 12706.7 A. (D1_U) |  | - | - | - | - | - | - | - | - | - |
| 9 | SSS249 | 11633 A. (QI-34) | 11949 A. (QI-34) | 12404 A. (QI-12) | 12626.2 A. (QE_34) |  | - | - | - | - | - | - | - | - |
| 10 | SSS630 | 5800 A. | - | - | - | - | - | - | - | - | - | - | - | - |
| 11 | MBAR2229 | 10622.4 A. (D1-U) | 12286.8 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - |
| 12 | MBAL3643 | 11088.3 A. (D2_U) | 11374.1 A. (D1-U) | 12007 A. (D1_L) | 12733 A. (D1_L) | 12850 A. | - | - | - | - | - | - | - | - |
| 13 | MBBL1189 | 12351.8 A. (D2_U) | 12512 A. (D1-U) | 12530.2 A. (D1-U) |  | - | - | - | - | - | - | - | - | - |
| 14 | MBAR1253 | 11003.7 A. (D2-L) | 12611.2 A. (D2-L) | 12768 A. (D2_U) |  | - | - | - | - | - | - | - | - | - |

Back to Homepage | For print

Shows  SSSS work on B1 & D2  & cohabitation with B2 & D1  (arc-SSS) ;  why long disconnection on 1261 A2 ?

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_11_A | TBC2 | Unable to launch hf DAQ during diode test on MB2071. | AB/CO | hf | Guy called AB/CO support. Software bug. A lab-view application vi was still running. |
| Tuesday_11_A | TBC2 | PC fault displayed showing too many valves opened, impeding to launch the training. Same fault displayed on TBA and TBF | AB/CO | hf | Guy came PLCCU in TEMA mode and has inhibited the access of the test. PLCCU put in local mode. This mode is not safe: Warning not connect more that 3 power supplie at the same time. A.Siemko is looking into the problem. |
| Wednesday_12_M | TBE1 | MB2229: HV test cold initial before test, connected to CFB failed at dipole versus ground and quench heater versus ground @1800 V. Rack used was MY92. Test @600V pass OK. | ICS |  | Pierre called. IFS box opened. Electric arc happened during a trial. ICS was asked to remove and change the IFS box, Problem remained the same with IFS box replaced. ICS will change the IFS box again. |
| Wednesday_12_M | TBC2 | MB2071: Tau Jump significant seen during training quench. | MTM |  | Pierre called. |
| Wednesday_12_M | TBC2 | Interlock on water impeding to launch training quench. | MTM |  | Check done: Water flow insufficient in the power supply. |
| Wednesday_12_A | TBF2 | HV test on MB1253 using MY92: the PLC -HV is showing communication error with the server. Not enough HV rack available to perform the five HV tests queuing (2 racks are working, MY93 is stopped). | AB/CO | HV | Test OK with MY95. MY92 was also OK. 2/3 racks available. |
| Friday_14_A | TBC2 | MB2055: errors during IAP @warm on LF heaters discharge. Error1: Quench heater tmin H2 and tmin H3 values are high, 1614 and 1642 respectively. Error2: Vanaode and Vcathode values both are @ - 1.01. | MTM | IAP | Guy informed. |
| Friday_14_A | TBF2 | IAP at warm: Vanaode and Vcathode values both are @ - 1.01 | MTM |  | Guy informed. An adaptator need to be installed for Magnet with left polarity since the beginning of the tests. |
| Friday_14_A | TBC2 | MB1278: Quench during SPA test at 12000 A.Power converter tripped. | AB/PO |  |  |
| Friday_14_N | TBC2 | VSupra Ext and VClamp Ext was permanent trigger on this card.. | ICS |  | ICS has been informed to check connection. |
| Friday_14_N | TBD2 | Confusion in the injection value for the SSW transfer function measurements | MTM |  | Stephane’s comment: The correct value is that of the TO DO LIST i.e. 265 A. This is the new value defined by the MEB in August 2005 for the MQM AT 1.9 K. It replaced the old value of 350 A. |
| Saturday_14_N | TBB1 | SSS654: Superconducting wires for correctors are too short (5cm missing) on magnet side. ICS team can't solder them to CFB side. | MTM |  | Guy and TC informed. No need to connect 600 A bus bar for S4 magnets. |
| Sunday_15_M | TBB2 | SSS049: IAP at warm : too low voltage value across the EF circuit i.e. 1 mV instead of 14 mV | MTM |  | Guy informed. ICS checked the connection. Short installed for previous magnet still installed. OK to proceed with the tests. |
| Sunday_15_N | TBA2 | Shafts 27/28 are scratching during rotation. MM2 on MB1265: Over-ranges in sector 02/03. | MTM |  | Problem solved: Protecting cover is touching the flat cable. Stephane advised to contact Maryline. Maryline and Fabienne found that the flat cable of the TRU was damaged. Stephane advised to change the TRU. |
| Sunday_15_N | TBB1 | SSS654 : Vclamp and V-Supra : permanent trigger found during IAP@warm. | ICS |  | ICS checked the connection again. 600 A bus bar not connected for S4 |
| Monday_16_M | TBF2 | MB2055: Jump in voltage going above the threshold. | MTM |  | Pierre advised to continue the training. |