### Week 24 starting 12 June 06

### SM18 Operation Meeting (Tuesdays) 13 June 06

Bench status  on Monday  12-06-2006 at:  6/12/2006 10:22:53 AM

| 3 | A1 | MBBR2290 | PT 1 IAP @ cold | 1.90 |
| --- | --- | --- | --- | --- |
| 7 | A2 | MBAL2335 | Prep 5 Cool Down | 169.58 |
| 12 | B1 |  |  | 299.02 |
| 6 | B2 | SSS649 | Prep 5 Cool Down | 297.68 |
| 8 | C1 | MBAR1332 | ICS 4 Final connection | 298.58 |
| 1 | C2 | MBAR1291 | PT 12 Warm Up | 290.17 |
| 4 | D1 | SSS659 | PT 6.1 Training 1 | 2.35 |
| 9 | D2 | SSS532 | Prep2.2C (EF clamp) | 299.65 |
| 10 | E1 | MBAR2329 | ICS 3 Traveller after warm test | 300.55 |
| 11 | E2 | MBAL2343 | ICS 1 WP04 HV Test Warm | 300.28 |
| 5 | F1 | MBAL2339 | PT 6.1 Training 1 | 4.18 HV |
| 2 | F2 | MBBR2262 | PT 12 Warm Up | 56.38 |

CONFIG :  D8- AS2 –IRSSS2;

Supervisor: Nikolay/        Eq support : 16-3602 :

16 Magnet Tests completed :  10 Dipoles (),  2 Arc-SSS  ( 038  REPEAT)

(16 Magnets in all)		1  500-series ( 513 (

3  600-series [ 633 (191 hrs),  690(152 hrs),  626  (149 hr) ]

2262 Special tests Pierre splice , 4K etc

General Points :

532 on D2 and preparation of SSW stages Thurs afternoon was not done

Else , SSW could have started on Friday & SIMCO survey done

Hence, 532 on D2 remained untouched for weekend  (

B1 kept free most of weekend for LH & cryo to repair on Monday

Issue of signing & instructions for D1 659 Friday night/Sat morning

Obstacle for shafts Install – ICS & etc… Sunday morn

- Change C cluster to SSS

- Situation from Cryogenics:  J-P Lamboy or ACR Rep.

- News /Situation from (SSS, SSSS)  :  J Halik

- Situation SSSS  :OP issues :

- A.O.B.

.

## Tests

| Magnets under Test from 04-06-2006 to 10-06-2006 |
| --- |
| - | Bench | Magnet | Shafts | + | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |  |  |
| 1 | TBA1 | MBBR1347 |  |  | 03-06-2006 | 51 h. | 20 h. | 20 h. | 20 h. | 17 h. | 09-06-2006 | 128 h. | Stripping |  |  |
| 2 | TBA2 | MBAR2314 |  |  | 31-05-2006 | 28 h. | 33 h. | 20 h. | 17 h. | 10 h. | 05-06-2006 | 108 h. | Stripping |  |  |
| 3 | TBA2 | MBBR2289 |  |  | 05-06-2006 | 22 h. | 21 h. | 30 h. | 19 h. | 12 h. | 10-06-2006 | 104 h. | Stripping |  |  |
| 4 | TBB1 | SSS038 |  |  | 01-06-2006 | 51 h. | 20 h. | 26 h. | 9 h. | 8 h. | 06-06-2006 | 114 h. | Stripping |  |  |
| 5 | TBB1 | SSS316 |  |  | 06-06-2006 | 28 h. | -15 h. | 51 h. | 7 h. | 13 h. | 10-06-2006 | 84 h. | Stripping |  |  |
| 6 | TBB2 | SSS513 |  |  | 05-06-2006 | 32 h. | 12 h. | 22 h. | 8 h. | 19 h. | 09-06-2006 | 93 h. | Stripping |  |  |
| 7 | TBB2 | SSS626 |  |  | 29-05-2006 | 31 h. | 35 h. | 25 h. | 7 h. | 51 h. | 05-06-2006 | 149 h. | Stand By |  |  |
| 8 | TBC1 | MBAL2341 |  |  | 31-05-2006 | 22 h. | 29 h. | 24 h. | 15 h. | 11 h. | 05-06-2006 | 101 h. | Stripping |  |  |
| 9 | TBC1 | MBBR1329 |  |  | 05-06-2006 | 23 h. | 28 h. | 24 h. | 13 h. | 15 h. | 10-06-2006 | 103 h. | Stripping |  |  |
| 10 | TBC2 | MBAR2330 |  |  | 04-06-2006 | 45 h. | 31 h. | 17 h. | 15 h. | 7 h. | 08-06-2006 | 115 h. | Stripping |  |  |
| 11 | TBD1 | SSS633 |  |  | 01-06-2006 | 47 h. | 12 h. | 73 h. | 9 h. | 50 h. | 09-06-2006 | 191 h. | Stand By |  |  |
| 12 | TBD2 | SSS690 |  |  | 29-05-2006 | 27 h. | 0 h. | 45 h. | 14 h. | 66 h. | 06-06-2006 | 152 h. | Stand By |  |  |
| 13 | TBE1 | MBAL2340 |  |  | 01-06-2006 | 24 h. | 23 h. | 18 h. | 15 h. | 34 h. | 06-06-2006 | 114 h. | Stripping |  |  |
| 14 | TBE2 | MBAR2273 |  |  | 02-06-2006 | 44 h. | -44 h. | 87 h. | 15 h. | 15 h. | 07-06-2006 | 117 h. | Stripping |  |  |
| 15 | TBF1 | MBBR1351 |  |  | 03-06-2006 | 23 h. | 45 h. | 37 h. | 15 h. | 17 h. | 09-06-2006 | 137 h. | Stripping |  |  |
| 16 | TBF2 | MBBR2262 |  |  | 02-06-2006 | 37 h. | 28 h. | 122 h. | 17 h. | 0 h. | 10-06-2006 | 204 h. | Not Found or Thermal cycle |  |  |

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBBR1347 | 12697 A. (D2_L) | 12689 A. (D2_U) | 12850.8 A. (D2-L) |  | - | - | - | - | - | - | - | - | - |
| 2 | MBAR2314 | 12000.7 A. (D2-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 3 | MBBR2289 | 11215.1 A. (D1-L) | 11922.9 A. (D2-U) | 11964.7 A. (D1-L) | 12377.5 A. (D1_L) | 12738.2 A. (D2-U) | 12714.8 A. (D1-L) | 12837.1 A. (D1_L) | 12853 A. | - | - | - | - | - |
| 4 | SSS038 | 12850 A. | - | - | - | - | - | - | - | - | - | - | - | - |
| 5 | SSS316 | 12126.2 A. (QE-34) | 12486.7 A. (QE-12) | 12790.6 A. (QI_12) |  | - | - | - | - | - | - | - | - | - |
| 6 | SSS513 | 12002.7 A. (E-34) | 12191.6 A. (QI-12) | 12693.5 A. (QE-12) |  | - | - | - | - | - | - | - | - | - |
| 7 | SSS626 | 5713.7 A. (Int MQML) | 5820 A. | - | - | - | - | - | - | - | - | - | - | - |
| 8 | MBAL2341 | 11234 A. (D1-L) | 12284.3 A. (D1_L) | 12624.3 A. (D1_L) |  | - | - | - | - | - | - | - | - | - |
| 9 | MBBR1329 | 11878.4 A. (D1_L) | 12282.7 A. (D2_L) | 12489.2 A. (D2-U) |  | - | - | - | - | - | - | - | - | - |
| 10 | MBAR2330 | 12427 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |
| 11 | SSS633 | 3544 A. (INT_34) | 3701.5 A. (Int-34) | 3734 A. (E_MQY12) | 3801 A. (MQY_I_34) | 3834 A. (MQY_E34) | 3847.2 A. (E_MQY_12) | 3864.4 A. (I-MQY_12) | 3877.4 A. (Ext. 12) | 3891.9 A. (E_MQY_12) | 3900 A. | - | - | - |
| 12 | SSS690 | 5485 A. (I-MQM2) | 5820 A. | - | - | - | - | - | - | - | - | - | - | - |
| 13 | MBAL2340 | 11956.3 A. (D2 - U) | 12498.8 A. (D2-L) | 12849.3 A. (D1_U) |  | - | - | - | - | - | - | - | - | - |
| 14 | MBAR2273 | 11012.4 A. (D2_U) | 12333.1 A. (D1_U) | 12746.4 A. (D2_L) |  | - | - | - | - | - | - | - | - | - |
| 15 | MBBR1351 | 11573.6 A. (D1-L) | 12612.1 A. (D2-U) | 12598 A. (D1-L) |  | - | - | - | - | - | - | - | - | - |
| 16 | MBBR2262 | 11631.9 A. (D2_L) | 12755 A. (D2-L) | 12044.2 A. (D2-L) | 12541.8 A. (D2-L) | 12723.1 A. (D2_L) | 12714.4 A. (D2_L) | 12596.8 A. (D2LMRB05) | 12537.2 A. (D2LMRB05) | 12608.7 A. (D2_L_S05) |  | - | - | - |

Effective 16 magnets Tested this week

2262 Long Special tests (pierre) at 4K now under  ROBTC,

633 usual reasons of connections /disconnections & powering +SSW + TRU MM ,    690, 626 , usual disconnection/removal logistics

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_06_M | TBB1 | SSS038: Traveler paper not found, | ICS? |  | J.Halik informed. He will call the responsible of SSS transport in 904 |
| Tuesday_06_N | TBB1 | SSS316: MOBIC Scanner could not read anti-cryostat barcode. Barcode is missing. | MTM |  | Anti-cryostat barcode entered manually. |
| Wednesday_07_A | TBA2 | MB1347: Alarms in provoked quenches PT5.1. DirVT noise exceeds 15V. | MTM | AQA | Giorgio advised to go on with PT5.2. The problem persisted. Then Giorgio changed a Potaim card and asked to repeat PT5.2. If OK, repeat 5.1. If problems persist, he advised to call Maryline or TC. Problems in provoked quenches PT5.1 and 5.2 solved then the tests were repeated. |
| Thursday_08_M | TBF2 | MB2262 : Special test at 4.55 K. DRQ55 at 1350 mbars: quench at 137A ! wrong manipulation?. | MTM |  | Quench to be repeated. |
| Thursday_08_M | TBF2 | MB2262 : Cryo problem. DRQ@20A/s#4 could not be done | ACR |  | ACR team solved the problem. |
| Thursday_08_A | TBB2 | Recurrent problem about HV panel with is not displayed in control room. | AB/CO | HV | Solved by A. Raimondo and Richard. He corrected the bug on cluster B and this version will be copied to all other clusters. |
| Thursday_08_A |  | Rack MY93.: BNC connector damaged. | MTM |  | Repaired by Richard. |
| Thursday_08_A | TBD2 | SSS532: Special test with SSW at warm. No program available. | MTM |  | TC tried to contact Guy at ~18.00 Hrs with no success and Juan. Marco informed. He stated that he will organize with Guy the test tomorrow morning. |
| Thursday_08_N | TBD2 | SSS532: Still problem with IAP at warm for 5XX series (correctors and MQ). | MTM | IAP | Giorgio informed Friday Morning. Giorgio repeated the measurement myself this morning, without any change, feeding 1 A into CD and EF correctors, and the 2 test were successful on the first trial. That means IAP software is working properly (files qe06 and qf03). Giorgio advised to do the measurements with dedicated attention. |
| Thursday_08_N |  | Note from the shift leader: A lot of little equipment is missing on benches (TBB / TBD) for measurements as Plexiglas cover / screws / small screw driver for potaim cards / thermometer & hygrometer in HV racks. | MTM |  | Action Richard. OP-team and ICS: do not spread Plexiglas cover. Screw drivers: action Jackie? |
| Thursday_08_N | TBE1 | MB2302: Quench Heater Voltage Minimum Energy reading front connector is broken. Unable to increase the Voltage up to 6.80 V | MTM |  | Voltage read from the back of the QH power supply. F.Flamand repaired the connector. |
| Friday_09_M | TBB | SSS316: Training 1. No contact with PLCSE. | AB/CO |  | PLCSE reset. If I happens during normal hours do no reset and call J.Brahy. |
| Friday_9_A | TBB2 | SSS649 :Non standard connection for this S4. | ICS |  | Connection stopped. Mechanical connection not correct. No magnet available for test during the week end. Instruction for connection was transmitted by Giorgio to ICS. Connected by ICS. |
| Friday_9_A | TBD2 | SSS532: SSW at warm performed by Marco. SAG calibration needed. | MTM |  | Waiting for Guy Monday. Magnet in stand_by. |
| Friday_9_A | TBD1 | SSS659: message from OP team. Do not sign any paper/electronic traveller, carryout prep2.2/2.3 and 3 and put the result on the paper on the bench. | MTM |  | On saturday MTM mechanic Team will close the magnet based on the result of warm test. |
| Friday_9_A | TBE2 | MB1355 : Two cables from the back of the QH supply rack were found connected to the multimeter for QH minimum energy voltage, instead of the tapping from the front side. While doing the PTE, it was noticed that minimum energy voltage was indicated with this new connection only, and not with the conventional tapping from the front. | MTM |  | Reason: Reading of Voltage is not working well. Problem already mentioned last week. |
| Friday_9_A | TBE2 | MB1355: LF acquisition panel in the local sun station was indicating "Ext Trigger Main LF", instead of "Recording armed" after saving the data followed by the tests. However files were generated correctly during the tests. | AB/CO | LF | Equip.support contacted before starting the training. |
| Friday_9_N | TBD1 | SSS659: Resistance measurement, values non conform.. | MTM |  | NC opened. Which template has been used? |
| Sunday_11_M | TBD2 | Traveler not signed because SSW at warm not done? | MTM |  |  |
| Sunday_11_M | TBA1 | MB2290: The stage of ref quad impedes to insert the shafts. ICS advised the shift leader. | MTM |  | Maryline and TC called. Ref quad removed. |
| Sunday_11_M | TBC1 | MB 1332: CDW1 HV Test could not be performed due to communication error between PLC HV and PLC SE. Also tried with changing HV rack. | MTM |  | Maryline informed. Problem is in the PLCSE cables. Action Richard Monday. Maryline advised to perform the test with ACR team being careful that the Temp will not change. Richard inspected the cable. Apparently no damage. He will wait for the next cold test (cryo conditions) to establish a clear diagnostic. |
| Sunday_11_N | TBA1 | MB2290: TRU Shaft on Ap1 is to be moved by hand ! The steering wheel is out of service | MTM |  | Giorgio informed : The problem of steering wheel will be corrected by Patrick. In between be gentle with the shaft movements. |
| Sunday_11_N | TBA1 | MB2290: T_coil values not correct | MTM |  | Giorgio informed: Calibration of some coefficients not correct. |
| Sunday_11_N | TBF2 | MB2262: PRQ @4.5 K is not listed in the folder “add new test”. | MTM |  |  |